## Sprint 1 (hidden)
# | Task | Estimate Hours | Estimate Amount, $ | Actual hours | Final price, $ | Status
| Study Vladimir's code, setup dev and test environments. Add 2FA (backend and frontend). | 32 |  | 40 | 1400 | Done
| Rewrite the docker files and deployemnt scripts. Deploy on the new server |  |  | 22 | 770 | Done
|  |  |  | Total | 2170

## Sprint 2 (ERC20 Epic) (hidden)
# | Task | Estimate Hours | Estimate Amount, $ | Actual hours | Final price, $ | Status
epic | EPIC - ERC20
26 | Add datastructure for storing data about tokens. Allow to query backend for the data | 36 |  | 20 | 700 | Done
27 | Add REST for CUD operations for the new data about tokens | 16 |  | 7 | 245 | Done
28 | Add database migration for ERC20 tokens | 4 |  | 4 | 140 | Done
30 | Add support to the frontend for the new backend methods | 16 |  | 9 | 315 | Done
31 | Make changes to trezorGetAddresses, trezorDistribute,trezorSweep | 24 |  | 30 | 1050 | Sweep not ready
29 | Change components on the existing forms to add support for adding and removing ERC20 | 20 |  | 19 | 665 | Done
32 | Add forms to support working with ERC20 lists (add admin interface to add, update,delete ERC20) | 24 |  | 24 | 840 | Done
|  |  |  | Total: | 3955

## Sprint 3 (hidden)
# | Task | Estimate Hours | Estimate Amount, $ | Actual hours | Final price, $ | Status
| Implement sweep for trezor and seed. | 10 |  | 10 | 350 | Done
| Improve usability (Mockups - ERC-20, check balances for all coins) | 40 |  |  | 0 | on approval
37 | Documentation and testing | 30 |  | 23 | 805 | In progress
39 | Adding Binance Smartchain | 8 |  | 8 | 280 | In progress (Trezor-Sweep doesn't work on BSC)
38 | Fixing custom path |  |  | 0 | 0 | Done
|  |  |  | Total: | 1435

## Sprint 4 (hidden)
# | Task | Estimate Hours | Estimate Amount, $ | Actual hours | Final price, $ | Status
37 | Documentation and testing. Adding technical description | 7 |  | 0 | 0 | move to Sprint 5
40 | Make Trezor - Sweep for BSC | 8 |  | 7 | 245 | done
41 | Test system with big numbers | 5 |  | 5 | 175 | done
47 | Bugs | 2 |  | 2 | 70 | done
Admin - Coins
42 | Remove 'Type' and add new logic in "Network" + Network combobox should be in the top | 4 |  | 4 | 140 | done
43 | Add Ability to changing nodes (websocket). Add new UI for adding networks, design data base, crate data base. Add field coin symbol. For Admin Add "Chain ID", "Gas limit", "IP node's", "Number of last block" | 20 |  | 22 | 770 | done
44 | Add precalculating Gas limit | 2 |  | 2 | 70 | done
45 | New logic for Naming. Banned to create the tokens with same names and automatically adding prefix of the network. Implement for backend and DB. Implement migration | 2 |  | 0 | 0 | Posponed
|  |  |  | Total: | 1470

## Sprint 4.1 (hidden)
# | Task | Estimate Hours | Estimate Amount, $ | Actual hours | Final price, $ | Status
48 | New fixes for custom path | 6 |  | 6 | 210 | done
| Bug: Fix fork in sweep | 2 |  | 2 | 70 | done
49 | Base Coin | 2 |  | 2 | 70 | done
50, 51 | Improve Gas | 24 |  | 16 | 560 | done
|  |  |  | Total: | 910

## Sprint 5 (hidden)
# | Task | Estimate Hours | Estimate Amount, $ | Actual hours | Final price, $ | Status
46 | Improve usability (Mockups - ERC-20, check balances for all coins, add new logic far naming tokens) | 60 |  | 4 | 140 | Pause
52 | Seed / Sweep calculating gas incorrectly (Gas limit) Analytics | 8 |  | 6 | 210 | Done
59 | Defining gas limit (parse our type transactions (10 last) from etherscan, take maximum and add 10% to this amount) | 4 |  | 4 | 140 | Done
54 | 2fa improve security: automatically redirect to login page | 6 |  | 5 | 175 | Done
55 | Naming and sorting | 3 |  | 3 | 105 | Done
|  |  |  | Total | 770

## Sprint 6 (hidden)
# | Task | Estimate Hours | Estimate Amount, $ | Actual hours | Final price, $ | Status
62 | EIP 1559 | 10 |  | 10 | 400 | Done, except trezor
| Fix bugs on prod, updating |  |  | 10 | 400 | Done
| Investigation precalculating with node |  |  | 14 | 560 | In progress
|  |  |  | Total | 1360

## Sprint 11 - main upadate (01.08 (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
1 | Fix bitcoinjs-lib usage in blockchain service |  | 7 | 245 | Done
2 | Fix withdraw tests |  | 2 | 70 | Done
3 | Fix deposit processing |  | 5 | 175 | Done
4 | Fix static code analysis tool used to flag programming errors |  | 6 | 210 | Done
5 | Updating info about currencies (main/test) |  | 1 | 35 | Done
6 | Using numeric id instead of uuid |  | 3 | 105 | Done
7 | Refactoring tests |  | 11 | 385 | Done
8 | Refactoring transfer chain processing |  | 20 | 700 | Done
9 | Adding new tests to cover important use cases |  | 5 | 175 | Done
10 | Adding system health check and failure notification |  | 8 | 280 | Done
11 | Adding sending notification for each deposit and withdraw |  | 10 | 350 | Done
12 | Deploying the crypto-payments project on the target machine, fixing some bugs/errors |  | 13 | 455 | Done
13 | Fix multiple kafka consumers |  | 10 | 350 | Done
14 | Fix decline withdraw notifications |  | 11 | 385 | Done
15 | Fix bookkeeper withdraw/deposit tests |  | 13 | 455 | Done
16 | Fix in merchant-api |  | 12 | 420 | Done
17 | Fix sighashtype/change processing/addressToScript for testnet bitcoin network |  | 10 | 350 | Done
18 | Fix withdraw strategies |  | 11 | 385 | Done
19 | Refactor blockchain boostrapping code |  | 10 | 350 | Done
20 | Extend GraphQL API |  | 7 | 245 | Done
|  | Total | 175 | 6125
|  | New Total | 64 | 2240
Improvement tasks
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
21 | Translation of code (partailly bookeeper and blockchain service) into a typed programming language TypeScript |  | 39 | 1365 | Done
22 | Transferring Ethereum to Goerli testnet (POW) |  | 1 | 35 | Done
23 | Fix transfer getting completed for manual withdraws |  | 2 | 70 | Done
24 | Make it possible to choose - either to repeat the failed hot payout, or to make a manual payout + front for repeating failed |  | 16 | 560 | Done
25 | Make new logic for calculating the balance of blockchain accounts to fix desynchronization of balances |  | 8 | 280 | Done
26 | Fix ethereum & BSC work fail which causes the system to stop |  | 7 | 245 | Done
27 | Wrong wallet selected during hot withdrawal |  | 2 | 70 | Done
28 | Fix the problem of two hot payout with the same sender and reciever |  | 6 | 210 | Done
29 | Fix the problem of non-deterministic payout processing |  | 14 | 490 | Done
30 | Fix system fail due to lack of balance during hot withdrawal |  | 1 | 35 | Done
31 | Discord hooks, grafana (healhcheck beginning) |  | 8 | 280 | Done
|  |  | Total | 3640

## Sprint 12 (24.10-25.11) (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
32 | New logic for the deposits |  | 12 | 420 | Done
33 | Updating rate in the moment of receiving funds |  | 3 | 105 | Done
34 | Calculate wallets funds, make Properties column, make Funds coloumn |  | 10 | 350 | Done
35 | Make new page with the comparing balances and wallets funds (only mock-ups in Sprint 2) |  |  | 0 | Mock-ups
36 | Hot payout issue |  | 8 | 280 | Done
37 | Update Bitcoin to use Segwit Address (compatible with MW and BIP32 we currently use to create address) | 56 | 24 | 840 | Done
|  |  | Total: | 1995

## Sprint 13 (28.11-13.12) (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
35 | Make new page with the comparing balances and wallets funds (only mock-ups in Sprint 2) |  | 11 | 385 | Done
41 | Use Extended Public Key to generate next available deposit address for Cold storage (Eliminates the need for uploading addresses, keep track of unused address, reduce errors) | 16 | 14 | 490 | Done
47 | optimize watching adrresses |  | 6 | 210 | In process
38 | Legacy to EIP1559 (can't change from the GUI) | 16 | 16 | 560 | Done
43 | Reset 2FA for merhant from admin pannel | 18 | 18 | 630 | Done
|  |  | Total | 2275

## Sprint 14 (14.12-26.12) (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
47 | optimize watching adrresses |  | 21 | 735 | Done
48 | Add extended public key and dereviation path to the deposit info window for the admin |  | 6 | 210 | Done
49 | Ability to download active addresses |  | 12 | 420 | Done
|  |  | Total: | 1365

## Sprint 15 (27.12-17.01) (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
50 | optimization and refactoring loading process |  | 12 | 420 | Done
51 | Integrate BPS with ZC |  | 15 | 525 | Done
52 | Alerting |  | 14 | 490 | Done
53 | Set up new fee source for ERC-20 |  |  | 0 | Done
54 | Fixes (cent to dollar in inputs Min,Max in Wallet-Edit, auto remove excess symbols in Wallet-Add addresses, Ethereum node failed) |  | 6 | 210 | Done
55 | Account Extended Public Key for ETH - xpub bip44 , BTC - ypub bip49 + validation |  | 4 | 140 | Done
56 | Segwit Wrapped BTC for payout (implement signing trxes) |  | 6 | 210 | Done
|  |  | Total | 1995

## Sprint 16 (18.01-10.02) (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
57 | Edit Wallets page (new coloumns, add searh, filters) | 16 | 14 | 490 | Done
58 | Add sums in dollars to the Indicators page, add favicon, fix refresh button on the Pending Payout page, add breadcrumb for user edit, edit text in tooltip threshold, fix accuracy bug | 9 | 9 | 315 | Done
59 | Security improvement. Checking permissions in GraphQL | 12 | 12 | 420 | Done
61 | Check isolation level for generating accounts from hierarchical keys | 8 | 8 | 280 | Done
62 | Race condition when editing merchant settings | 12 | 12 | 420 | Done
63 | Display the reason for the fall of the transaction on the interface on the Pending Payout page | 6 | 6 | 210 | Done
64 | Change logics for the calculating virtual balances, balance synchronizer, | 28 | 12 | 420 | In process
65 | make doc about "Pending payout and Failed transfers |  | 2 | 70 | Done
66 | Reconnect to the node |  | 14 | 490 | Done
67 | Admin creating issue |  | 1 | 35 | Done
68 | Improvement of Integration BPS with ZC (Deposit only) |  | 6 | 210 | Done
69 | Investigation the issue ETH payout on the stage |  | 4 | 140 | Done
|  |  | Total | 3500
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The admin panel does not check access rights to read fields, this is a potential security weakness

## Sprint 17 (11.02-28.02) (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
64 | Change logics for the calculating virtual balances, balance synchronizer, | 28(12) | 16 | 560 | Done
70 | Rewrite admin's microservice to TS | 16 | 16 | 560 | Done
71 | Using nice-gRPC for bookkeeper microservice | 16 | 20 | 700 | Done
79 | Add input for the coins to the Deposit, Payout | 4 |  | 0 | Posponed
80 | POST;GET /payout + deposit API update | 4 | 4 | 140 | Done
81 | Prohibition of creating payouts to deposit addresses | 3 | 3 | 105 | Done
82 | trace_id comes to webhook with null value | 2 | 2 | 70 | Done
83 | BPS is kicking user out very quickly from login | 2 |  | 0 | Posponed
84 | Change DataDog to GrayLog |  | 8 | 280 | Done
75 | Monitoring. Collecting traces with Opentelemetry (monitor possible optimize codebase) | 30 | 32 | 1120 | Done
85 | Monitoring. State of microservices |  | 6 | 210 | Done
|  |  | Total | 3745
11
10.28%

## Sprint 18 (01.03-23.03) (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
87 | Add a callback when Payout was moved in hot processing |  | 8 | 280 | Done
73 | Monitoring. Logging requests with axios | 6 | 6 | 210 | Done
74 | Monitoring. Collection request metrics from the node | 10 | 12 | 420 | Done
76 | Change the scenario of the errror duplicate transfers, when the last transfer was decline we shouldn't take into account it | 6 | 10 | 350 | Done
77 | Health monitor page |  |  | 0 | Declined
78 | make real balance coloumn in wallets + refresh button |  |  | 0 | Declined
86 | Create doc for Telemetry and Grafana, update deploy script? | 8 | 8 | 280 | Done
83 | BPS is kicking user out very quickly from login |  | 4 | 140 | Done
79 | Add input for the coins to the Deposit, Payout |  | 4 | 140 | Done
89 | Add hash for the payout which in SENT status |  | 9 | 315 | Done
90 | Edit Deposit api |  | 2 | 70 | Done
60 | Add a check against double processing so that there is no double addition of amounts. Sending to Kafka with Outbox Table. Without it rare inner events can be processed twice - for example doubling deposit | 35 | 18 | 630 | In process
91 | ETH processing problems : replacement transaction underpriced |  | 12 | 420 | Done
92 | Issue: BSC Scanner Loops Due to Forks |  | 8 | 280 | Done
93 | Update, resolve RAM issue |  | 4 | 140 | Done
|  |  | Total: | 3675
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In GitHub
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It would be good for us to explain here that we can either use usd_amount or coin_amount. The example should not show both options in the same schema

## Sprint 19 (24.03-09.04) (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
88 | Add a signature for callbacks |  | 4 | 140 | Done
60 | Add a check against double processing so that there is no double addition of amounts. Sending to Kafka with Outbox Table. Without it rare inner events can be processed twice - for example doubling deposit | 35 (18) | 17 | 595 | In process
72 | Monitoring. Discord hooks from grafana about nodejs service health-state | 10 | 10 | 350 | Done
94 | Request+hooks informativity improvement |  | 6 | 210 | Done
95 | Errors when handling events in bookkeeper |  | 8 | 280 | Done
96 | Frontend fixes: layout breaks on Wallet - New Wallet when selecting multiple admins; Pending payout page - Table headers jump on reload; |  | 3 | 105 | Done
| Restrict to use one adddress in different formats (ETH) |  | 6 | 210 | Done
| Fix ETH error "Transaction was not mined within 50 blocks" - if it got into the network, then we make the status pending and do not give it to manual - we wait. If gently, you can manually increase the nonce |  | 3 | 105 | Done
| investigated issue with BTC node |  | 4 | 140 | Done
| Made instruction how install BPS |  | 3 | 105 | Done
| Offchain deposit |  | 7 | 245 | Done
| Choosing a wallet with the closest balance, the same as the payout amount |  | 3 | 105 | Done
| JSON for currencies instead currency.db microservice |  | 8 | 280 | Done
| Check packages for vulnerabilities |  | 3 | 105 | Done
|  |  | Total: | 2975

## Sprint 20 (10.04-29.04) (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
| Parallel payouts (BTC with 10 sec delay) |  | 32 | 1120 | Done
| Add errors descriptions when trx fall into manual payout |  | 6 | 210 | Done
| Fix wallet balance, restrict make a payout to the payout addresses |  | 6 | 210 | Done
| Add new gas source - Etherscan |  | 5 | 175 | Done
| Create postman collection for auto test |  | 2 | 70 | Done
| Imrove node.js version (from 14 to 16) |  | 4 | 140 | In process
| Blockchain service stabilization |  | 17 | 595 | Done
| Bookkeeper service stabilization |  | 5 | 175 | Done
|  |  | Total: | 2695

## Sprint 21 (30.04-03.07) (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
| Using a JSON file for a currency database instead of SQLite |  | 10 | 350 | Done
| Add info about receiver address to the Payouts page |  | 3 | 105 | Done
| Force feauture | 18 | 20 | 700 | Done
| Add to the force window current max fee + amount in coins |  | 8 | 280 | Done
| Set DF, PF, MF for specific merchant for specific currency | 25 | 25 | 875 | Done
| Imrove force - add ability to change merchant fee in force window | 36 | 36 | 1260 | Done
| Add new coloumns and filters to Payots table (Type, Status ; type, max fee, mercahn fee in %) |  | 16 | 560 | Done
| Small fixes (add link to the graylog into details window on the Failed transfers page; edit transaltions; fix ETH USDT; make Tools-Wallets-Add address in alphabetic order; change calculation of the amount in the Reports-Payouts; disable discord about quantity of the deposits addresses; enable/disable RBF; fix issue on the Payout page; investigate why logs didn't work; logs analyze; add coloumns ID, Trace ID and serch field in the Deposits, Payouts pages; Max Fee for USDT (Ethereum) wrong; Hung transactions alerts; Max Fee value Fluctuates with market conditions; Error "has no matching Address" in Bitcoin |  | 22 | 770 | Done
| Check and fix work with LTC, BCH |  | 8 | 280 | Done
| Investigate issue with the wallets balance, create log scrypt |  | 10 | 350 | Done
| Fixing linter warnings |  | 12 | 420 | In process
| Change order in the Payouts and Deposits page, add new columns - Block, Time |  | 8 | 280 | Done
| Fix issue "has no matching Address" in Bitcoin, updated library |  | 20 | 700 | Done
| Add ability to retry trx payout, which are in the Pending payout page because in the moment of payout where was no enough money on the hot wallet |  | 16 | 560 | Done
| Make min fee for the BCH, LTC 1 satoshi |  | 2 | 70 | Done
| Fix "Non-bip68 final" and other issues in BTC when payout on the stage |  | 4 | 140 | Done
| Add discord hook about low balance on the hot wallet |  | 22 | 770 | Done
| Investigate the isuse - trx don't reach the mempool |  | 28 | 980 | Done
| Fix cold payout feature |  | 4 | 140 | Done
|  |  | Total: | 9590

## Sprint 22 (04.07-03.08) (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
| Move 2FA to header |  | 3 | 105 | Done
| Merchant MaxFee % to MaxFee $ |  | 17 | 595 | Done
| Add Merchant should move moved from Users to Merchants page |  | 3 | 105 | Done
| Choose Transaction Fee Priority |  | 33 | 1155 | Done
| Set up database backups |  | 9 | 315 | Done
| Updating nice-grpc generated files |  | 4 | 140 | Done
| Slow Payouts Page (delete option to show all trx on the one page, by default show only today trxs) |  | 12 | 420 | Done
| Set gas limit in the config file for the Ethereum network + investigate the issue |  | 14 | 490 | Done
| Issue investigation - Blockchain-worker Service Restarts Due to OOM |  | 5 | 175 | In process
| Move Add addresses functionality to Wallets + add addresses in the moment of create the wallet |  | 12 | 420 | Done
| Fixing linter warnings |  | 6 | 210 | In process
| Functional Tests for Bitcoin |  | 9 | 315 | Done
| Decline failed trx, consolidate Pending payouts, Failed transfers pages |  | 16 | 560 | Done
| Fix small issues |  | 6 | 210 | Done
| Server maintenance |  | 10 | 350 | Done
| Add an instant hook to the discord about failed transactions due to "Not enough funds on the wallet to pay out" |  | 9 | 315 | Done
|  |  | Total: | 5880

## Sprint 23 (04.08-04.09) (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
1 | Bug connection lost |  | 12 | 420 | Done
2 | Add front and back versioning |  | 5 | 175 | In process
3 | Balance Notifications Enhancement |  | 8 | 280 | Done
4 | Work flow of the Manual Payout feature |  | 11 | 385 | Done
5 | Balance no longer low |  | 7 | 245 | Done
6 | Compact Discord Messages |  | 4 | 140 | Done
7 | Instant discord hook for trx - Not enough balance, real fee is greater than max fee |  | 8 | 280 | Done
8 | Bug: Transaction amount did not match during retry |  | 3 | 105 | Done
9 | Activity log for the trxs (without open in window) |  | 20 | 700 | Done
10 | Add more fields to Pending Payouts |  | 4 | 140 | Done
11 | 2 Decimal Points |  | 1 | 35 | Done
12 | 0 should not be blank value |  | 2 | 70 | Done
13 | Force Bug Merchant 0% |  | 2 | 70 | Done
14 | Event from Kafka was not processed |  | 20 | 700 | Done
15 | Functional tests for Ethereum |  | 12 | 420 | In process
16 | Blockchain synchronization monitoring |  | 15 | 525 | Done
17 | Incorrect transaction status in discord hook |  | 3 | 105 | Done
18 | Add a Force option for transactions that fell due to min relay fee not met 225<226 (code 66) |  | 8 | 280 | Done
19 | Fixed logs on the test site |  | 1 | 35 | Done
20 | Fixed permission error (permission denied) on stage during update |  | 2 | 70 | Done
21 | Fixed problem - when updating, images are successfully collected, but old images are launched |  | 3 | 105 | Done
22 | Analysed of the problem, why the output of id 376 took a long time |  | 1 | 35 | Done
23 | Investigate why the transaction was sent 2 times BTC |  | 2 | 70 | Done
24 | Investigate why connection not establish error occurred for BTC |  | 2 | 70 | Done
|  |  | Total: | 5460
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On the prod bps01-prd-sjo, at the time the transaction was sent, there was a lag in blocks due to the fact that before that, in the period from 0:00 to 10:00 UTC, the system did not work, there was no collection of logs

## Sprint 24 (05.09-29.10) (hidden)
# | Task | Estimate Hours | Actual hours | Final price, $ | Status
528 | Merge BSC and ETH code (optimization task) |  | 14 | 490 | Done
496 | Functional tests for Ethereum - e2e tests (optimization task) |  | 16 | 560 | Done
553 | Correct API response in case of incorrect address |  | 3 | 105 | Done
563 | Snooze alerts if discord doesn't respond |  | 3 | 105 | Done
178 | Merchant Add Manual Payout Boolean |  | 3 | 105 | Done
564 | Creating a postman collection for load tests of deposits |  | 3 | 105 | Done
550 | Batch Transactions BTC, BCH, LTC |  | 49 | 1715 | Done
514 | Setting up Init services for initial deployment |  | 4 | 140 | Done
179 | Add Shortname for Merchs |  | 8 | 280 | Done
11 | Moving to traefik |  | 4 | 140 | Done
176 | Deposits: Handle wrong blockchain or token sent (ETH token) |  | 24 | 840 | Done
13 | Make it possible to display versioning without nginx |  | 2 | 70 | Done
562 | Investigating the "Incorrect ETH Fee" issue |  | 4 | 140 | Done
12 | Add an option to restart containers in the script |  | 1 | 35 | Done
548 | Add Tron BC |  | 50 | 1750 | Done
559 | Small fixes 1 (Investigating, why the blockchain service will restart in production; creating insturcions in .MD; Checking logs, why Binance is not working; fix error on the stage when going to the dashboard, Make logs in the window) |  | 10 | 350 | Done
547 | Small fixes 2 (Investigating logs - 30 deposits were made for production, only 2 passed; Investigating issue in bps_deploy script running 7; Creating a remove currency script to remove a currency from the database, Change alert text Could not find account; Add 8 character limit for wallet nickname; Solving the problem with access rights on xhain; Add the ability to sort by time on the Payout page) |  | 12 | 420 | Done
174 | Add a consaolidation fee column to the Deposits table |  | 1 | 35 | Done
175 | Add search by transaction ID in Deposits and Payouts |  | 1 | 35 | Done
549 | Add new currencies |  | 1 | 35 | Done
167 | Create a Dashboard Page |  | 18 | 630 | Done
169 | API Key managment and IP Whitelisting |  | 20 | 700 | Done
546 | Track Consolidation fee |  | 8 | 280 | Done
554 | Add Polygon BC |  | 20 | 700 | Done
|  |  | Total: | 9765
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Make a common repository that will accept a model for blocks and a model for transactions Make a general block scanner, because... The logic for downloading blocks is the same, only the model names differ Create a common interface for interaction with the node, because they run on top of web3
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Often people request a deposit, for example, in USDT Ethereum, and replenish the deposit in ETH. William wants to be able to count these payments. To do this, we add the ability for the administrator to make a replacement (Replace). To do this, on the deposits page, the admin must click Details, and in the window that opens, click Replace.
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total: the problem is in the node, namely in the version of the node. Calling the eth_getBlockByNumber method returns different results: in the new version, gasPrice is equal to maxPriorityFeePerGas, in the old version, gasPrice is exactly the final price for gas. The correction is as follows: take the effectiveGasPrice value from the result of calling the eth_getTransactionReceipt method as the final gas price (the result is the same in two versions)
Note on B21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add: Ethereum USDC Ethereum SHIB Ethereum LINK Ethereum TUSD Ethereum PYUSD Binance BUSD Delete: BNB-Peg Bitcoin BNB-Peg-Ethereum BNB-USDT

## Sprint 25 (30.10-28.12) (hidden)
№ | Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) | 82 | 30 | 2460
2 | Max (PM) | 36 | 25 | 900
3 | Ksenia (Analytic) | 33 | 25 | 825
4 | Philipp (Lead) | 80 | 50 | 4000
5 | Backend developer 1 | 277.5 | 40 | 11100
6 | Backend developer 2 | 51 | 40 | 2040
7 | Frontend developer 1 | 64 | 35 | 2240
8 | Frontend developer 1 | 86.5 | 35 | 3027.5
9 | Designer | 70 | 25 | 1750
28342.5
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Final price, $
1 | Create a doc for LadyLee |  |  | 4 |  |  |  | 200
2 | Invoice design | 10 | 25 |  |  |  | 70 | 2750
3 | Check and fix transaction isolation |  |  | 1 | 6 |  |  | 290
4 | Change the wallet name selection algorithm |  |  |  | 1 |  |  | 40
5 | Color highlighting of sections correction |  |  |  |  | 2 |  | 70
6 | Invoice Backend: | [6 empty] | 0
| Main invoice backend |  |  | 38 | 267.5 |  |  | 12600
| Sew up exchange rates in exchange service migration |  |  | 1 | 5 |  |  | 250
| invoice & deposits logs |  |  |  | 8 |  |  | 320
| Invoices rates optimise |  |  |  | 5 |  |  | 200
| Overpaid/underpaid transactions fix (invoices) |  |  |  | 6 |  |  | 240
7 | Invoice Customer UI: | [6 empty] | 0
| Main invoice frontend | 7 | 16 | 20 |  | 92.5 |  | 4892.5
| QR code transfer url | 1 |  |  |  | 10 |  | 375
| UI improvments | 1 |  | 4 |  | 15 |  | 750
| check freezed rate |  |  |  |  | 5 |  | 175
8 | Max Fee Improvements |  |  |  | 19 | 7 |  | 1005
9 | Invoice Admin UI: | [6 empty] | 0
| Main admin frontend | 5 | 2 | 2 | 11 | 15 |  | 1250
| UI improvments |  |  |  |  | 4 |  | 140
10 | Invoice BA | 20 | 30 | 5 |  |  |  | 1650
11 | Blockfils BA | 10 | 3 | 2 |  |  |  | 440
12 | Smart accumulation BA | 10 | 3 | 1 |  |  |  | 390
13 | Deposits: Handle wrong blockchain or token sent (BTC-BCH) BA | 3 | 1 | 1 |  |  |  | 155
14 | Merchant Passthrough Fee BA | 2 | 2 | 1 |  |  |  | 160
28342.5
| Main tasks | 26912.5
| Additional tasks | 1430

## Sprint 26 (29.12-06.03) (hidden)
| Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) | 88 | 30 | 2640
2 | Max (PM) | 72 | 25 | 1800
3 | Ksenia (Analytic) | 39 | 25 | 975
4 | Philipp (Lead) | 60 | 50 | 3000
5 | Backend developer 1 | 232 | 40 | 9280
6 | Backend developer 2 | 41 | 40 | 1640
7 | Frontend developer 1 | 66 | 35 | 2310
8 | Frontend developer 1 | 58 | 35 | 2030
9 | Designer | 0.5 | 25 | 12.5
23687.5
|  | Actual | [6 empty] | Estimation
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Actual price, $ | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $ | Status
1 | BA tasks from backlog | 36 | 40 |  |  |  |  | 2100 | 62 | 27 |  |  |  |  | 2360 | Done
2 | Invoice alerts to the discord | 1 |  | 1 | 5 |  |  | 275 | 1 |  | 1 | 6 |  |  | 315 | Done
3 | Create Invoice documentation | 5 | 2 |  |  |  |  | 185 | 6 | 2 |  |  |  |  | 210 | Done
4 | Deposits: Handle wrong blockchain or token sent (BTC-BCH) | 2 | 1 | 5 | 24 | 4 |  | 1430 | 2 |  | 5 | 36 | 4 |  | 1880 | Done
5 | Delete the time of the last batch in the wallet | 2 |  |  | 3 |  |  | 170 | 2 |  |  | 5 |  |  | 250 | Done
6 | BLOCKFILLS: Merchant exchange Coin or Token automatically | 24 | 22 | 22 | 100 | 34 |  | 7550 | 32 | 10 | 18 | 104 | 31 |  | 7245 | Done
7 | Created 100 deposits with exact coin amount | 2 | 1 | 1 | 7 |  |  | 410 | 2 |  | 1 | 5 |  |  | 300 | Done
8 | Auto accumulation | 22 | 16 | 14 | 78 | 16 |  | 5410 | 24 | 20 | 13 | 88 | 15 |  | 5895 | Done
9 | Moving the pending payouts section | 3 |  |  |  | 5 | 0.5 | 262.5 | 3 |  |  |  | 3 |  | 180 | Done
10 | Update npm packages | 1 |  |  | 5 |  |  | 225 | 1 |  |  | 5 |  |  | 225 | Posponed
11 | Download Transaction Details in CSV | 2 | 1 | 2 | 5 | 12 |  | 800 | 2 |  | 2 |  | 10 |  | 500 | Done
12 | Scanners optimization of ethereum based blockchains | 1 |  | 2 | 8 |  |  | 445 | 1 |  | 2 | 10 |  |  | 525 | Done
13 | Small technical stuff - 599) /packages/blockchain/src/commandHandlers/processTransactionHandler.js#L225 should be inside transaction 448) Ethereum's eth_getTransactionReceipt can goes to infinity recursion. Need to fix it. Solution - raised the version of the web3 library to 4.4 569) system doesn't work without Graylog. Big chance that we cannot handle it, but let's investigate. Result - we investigate a variants how better do it 604) Investigating the kafka issue when discord hooks are 0.5-1 hour late. Solution - subscribe to Kafka topics without using regex 609) Making block scanners separate services 602) Retry failed serializable trxs in blockchain service | 4 | 4 | 9 | 25 | 20 |  | 2370 | 4 | 1 | 8 | 66 |  |  | 3170 | Done
14 | Add "actual fee" to logs // Max fee did not work for BTC transactions 11/29/2023 | 1 |  | 1 | 10 | 2 |  | 545 | 1 |  | 1 | 8 | 2 |  | 465 | Done
15 | Log user actions (only Front-end actions) | 5 | 1 | 3 | 3 | 31 |  | 1510 | 5 | 1 | 3 | 31 | 10 |  | 1895 | Done
0
0
0
0
0
0
0
0
0
0
0
[8 empty] | 23687.5 | [6 empty] | 25415
| Main tasks | 17890
| Additional tasks | 5797.5

## Sprint 27 (07.03-26.04) (hidden)
№ | Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) | 80 | 30 | 2400
2 | Max (PM) | 69 | 25 | 1725
3 | Ksenia (Analytic) | 19 | 25 | 475
4 | Philipp (Lead) | 50 | 50 | 2500
5 | Backend developer 1 | 176 | 40 | 7040
6 | Backend developer 2 | 60.5 | 40 | 2420
7 | Frontend developer 1 | 50 | 35 | 1750
8 | Frontend developer 1 |  | 35 | 0
9 | Designer | 2.5 | 25 | 62.5
18372.5
|  | Actual | [6 empty] | Estimation
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Actual price, $ | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $ | Status
1 | Calculate GasLimit rather than using static 60k |  | 2 | 0.5 | 5 |  |  | 285 | 1 | 1 |  | 6 |  |  | 295 | Done
2 | Integration WPB to BPS | 3 | 4 | 2 | 14 |  |  | 855 | 1 | 1 | 2 | 16 |  |  | 795 | Done
3 | Deposit Address Upgrades | 4 | 2 | 2 | 24 |  |  | 1220 | 4 |  | 3 | 24 |  |  | 1210 | Done
4 | Force Transaction when Mempool down | 1 | 0.5 |  | 4 | 1 |  | 235 | 2 |  | 1 | 6 | 3 |  | 445 | Done
5 | Temporary Address more than 1 deposit | 5 | 4 | 6 | 42 | 6 |  | 2435 | 5 | 2 | 2 | 16 | 6 |  | 1135 | Done
6 | BEAUTIFICATION 2024-02 | 8 | 7 | 4 | 6 | 20 | 2.5 | 1612.5 | 6 | 2 | 3 | 7 | 26 |  | 1550 | Done
Add new logic of filter block
Replace $xxxx.xx with xxxx.xx USD
Change color of Network Fee
Change date and time formatting
Privacy of Extended key in Deposit Info
% Merchant Fee add 1 decimal
Refresh Button
Short Name usage Improvements
Date field is too small for current dates
7 | PAYOUTS/DEPOSITS: search by Address | 2 | 1 | 3 | 12 | 5 |  | 885 | 2 |  | 1 | 8 | 6 |  | 630 | Done
8 | Manual exchange (Swap) | [6 empty] | 0 | 15 | 10 | 7 | 42 | 26 |  | 3615 | Posponed
9 | BA tasks from backlog | 43 | 45 | 4 |  |  |  | 2625 | 40 | 18 | 4 |  |  |  | 1740 | Done
10 | Update npm packages |  |  |  | 2 |  |  | 80 | 1 |  |  | 2 |  |  | 105 | Done
11 | Small technical staff | 3 |  | 5 | 42 | 3 |  | 2110 | 3 |  |  | 20 | 10 |  | 1225 | Done
12 | BF Improvements
| Allowed currecies tables | 3 | 1 | 2 | 9.5 | 10 |  | 935 | 4 | 1 | 4 | 9 | 10 |  | 1040 | Done
| BF logic imrovements | 4 | 4 | 8 | 24 | 2 |  | 1650 | 6 | 2 | 5 | 26 | 2 |  | 1570 | Done
[7 empty] | Subtotal: | 14927.5 | [5 empty] | Subtotal: | 15355
Added tasks | [13 empty] | Subtotal: | 11740
13 | BF Improvements
| Start of unification of system Exchange process for the possibility of expansion and connection of new exchange providers. Making basis in codebase according developped diagram of Exchange \ Swap processes | 4 | 4 | 10 | 18 |  |  | 1440 | Done
| Independence of the system from the exchange service + notification in discord, if ES not answered | 3 | 1 | 1 | 14 |  |  | 715 | Done
14 | Pending and Failed Tabs do not refresh | 2 |  |  | 5 |  |  | 250 | Done
15 | Login 2FA Mandatory to access web app | 1 | 4 | 1.5 | 9 | 3 |  | 685 | Done
16 | Small fixes | 2 | 0.5 | 1 | 6 |  |  | 355 | Done
[7 empty] | Subtotal: | 3445
[7 empty] | TOTAL: | 18372.5

## Sprint 28 (27.04- 28.06) (hidden)
№ | Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) | 69 | 30 | 2070
2 | Max (PM) | 89 | 25 | 2225
3 | Ksenia (Analytic) | 9 | 25 | 225
4 | Philipp (Lead) | 30 | 50 | 1500
5 | Backend developer 1 | 197 | 40 | 7880
6 | Backend developer 2 | 115 | 40 | 4600
7 | Backend developer 3 | 40 | 40 | 1600
8 | Frontend developer 1 | 85 | 35 | 2975
9 | Frontend developer 2 |  | 35 | 0
10 | Designer | 9 | 25 | 225
23300
|  | Actual | [6 empty] | Estimation
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Actual price, $ | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $ | Status
1 | BA tasks from backlog | 41 | 43 | 2 |  |  | 4 | 2515 | 40 | 30 |  |  |  |  | 1900 | Done
2 | REPORTS | [6 empty] | 0 | [6 empty] | 0
| Running balance | 8 | 4 | 5 | 40 | 25 | 5 | 3170 |  |  | 10 | 60 | 60 |  | 5000 | Done
| Deposit control (consolidator and admin view) | 4 | 2 |  | 40 | 15 |  | 2285 | [6 empty] | 0 | In process
| Payout control | [6 empty] | 0 | [6 empty] | 0 | In process
| Tags | 1 |  |  | 3 |  |  | 145 | [6 empty] | 0 | In process
| Consolidator assigning | 2 |  |  | 14 |  |  | 610 | [6 empty] | 0 | In process
| Add new user type Accountant, Consolidator | 1 |  |  | 5 |  |  | 225 | [6 empty] | 0 | In process
3 | System optimizations after high load tests | 2 |  | 5 | 65 |  |  | 2900 | [6 empty] | 0
4 | Investigate USDT over TON | 1 |  |  | 10 |  |  | 425 | 5 |  | 2 | 25 |  |  | 1225 | In process
5 | Added 2FA securuty to any actions | 4 | 1 | 1 | 28 | 10 |  | 1650 | 6 |  | 2 | 16 | 8 |  | 1170 | Done
6 | For API keys need to make a whitelist for requests | [6 empty] | 0 | [6 empty] | 0 | Done
7 | Payout Pending Grouping + 2FA | 2 | 1 | 1 | 10 | 15 |  | 1055 | 6 |  | 3 | 8 | 20 |  | 1320 | Done
8 | Small fixes: 231) Change 1:15' 34'' into 1h 15' 34'' 236) Change the order of coin and USD 246) Fix sorting (the sorting sometimes swaps 2 rows) 710) Change delimiter from semicolon to comma 255) Fix layout (tools➝actions) 712) Prohibit to create offchain payouts in debt 635) Fix replace old transactions 727) Change the status for old extended transactions 717) Handle deposit with BF exchange if pair isn't exist | 10 | 4 | 2 | 20 | 5 |  | 1445 | 2 | 2 | 1 | 5 |  |  | 360 | Done
9 | Small technical staff 636) Javascript ➝ Typescript Users service 711) Save the reference currency for swaps 713) Add additional check for positive amounts in Bookkeeper service 709) Optimization rate's requests 639) Javascript ➝ Typescript blockchain service 718) Save invoice address for running balance 704) Broken balances after stress-test 701) Serialization issue 700) Parsing issue |  | 4 | 5 | 46 |  |  | 2210 | 10 | 5 | 5 | 40 |  |  | 2250 | Done
10 | Manual Swap + add general logic from the diagram | 8 | 4 | 8 | 48 | 15 |  | 3165 | 12 |  | 9 | 64 | 26 |  | 4220 | Done
11 | Process stucked pending transaction automatically if was already sent to node (Script of loading the BTC node) |  |  |  | 7 |  |  | 280 |  |  | 1 | 15 |  |  | 650
0
0
0
0
0
0
0
0
0
0
0
0
[7 empty] | Subtotal | 22080 | [5 empty] | Subtotal | 18095
Added tasks | [8 empty] | Status
12 | Fix download CSV (high load) | 1 | 1 |  | 12 |  |  | 535 | Done
13 | Find the reason why is there a difference in deposits between WPB and BPS | 12 | 4 | 1 | 2 |  |  | 550 | Done
14 | Issue: Payout for the one address | 1 | 1 |  | 2 |  |  | 135 | Done
[7 empty] | Subtotal: | 1220
[7 empty] | TOTAL: | 23300
Note on F24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: to 16.05 we have used 40 hours, if everything goes according to the positive scenario, we will need another 60 hours

## Sprint 29 (01.07 - 13.08 ) (hidden)
№ | Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) | 46 | 30 | 1380
2 | Max (PM) | 118 | 25 | 2950
3 | Kostya (Analytic) | 24 | 25 | 600
4 | Philipp (Lead) | 20 | 50 | 1000
5 | Backend developer 1 | 90 | 40 | 3600
6 | Backend developer 2 | 161.5 | 40 | 6460
7 | Backend developer 3 | 25 | 40 | 1000
8 | Frontend developer 1 | 142 | 35 | 4970
9 | Frontend developer 1 |  | 35 | 0
10 | Designer |  | 25 | 0
21960
|  | Actual | [6 empty] | Status | Estimation
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $ |  | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $
1 | REPORTS | [6 empty] | 0 |  | 16 | 4 |  |  |  |  | 520
| Deposit control (consolidator and admin view) | 6 | 6 | 6 | 37 | 45 |  | 3685 | Done |  |  | 16 | 80 | 80 |  | 6800
| Payout control | 3 | 2 | 2 | 28 | 26 |  | 2265 | Done |  |  | 6 | 32 | 40 |  | 2980
| Tags | 3 | 2 | 2 | 17 | 18 |  | 1545 | Done |  |  | 4 | 20 | 16 |  | 1560
| Consolidator assigning | 3 | 2 | 2 | 12 | 12 |  | 1135 | Done |  |  | 3 | 16 | 16 |  | 1350
| Add new user type Accountant, Consolidator | 3 | 2 | 2 | 35 | 15 |  | 2160 | Done |  |  | 6 | 40 | 26 |  | 2810
2 | Merchant View Updates (Payouts Remove Max Fee, Payouts Remove Logs, Tools Remove Actions, Payouts Remove Network Fee, Deposts Remove Consolidation Fee) | 3 | 1 | 1 |  | 4 |  | 295 | Done | 4 | 1 | 1 |  | 16 |  | 740
3 | Documentation | [6 empty] | 0 | [7 empty] | 0
| Create services and containers technical documentation |  |  |  | 7 |  |  | 280 | Done |  |  |  | 4 |  |  | 160
| Create merchant guide | 30 | 6 |  |  |  |  | 930 | Done | 40 | 8 |  |  |  |  | 1240
| Create admin guide (short) | 24 | 2 |  |  |  |  | 660 | Done | 16 | 2 |  |  |  |  | 460
4 | Add human-readable API error description | 3 | [5 empty] | 75 | Posponed | 4 |  | 4 | 40 |  |  | 1900
5 | Testing | [6 empty] | 0 | Done | 20 | [5 empty] | 500
6 | Dashboard updates | 4 |  | 1 | 15 | 6 |  | 960 | Done | 5 |  | 3 | 24 | 8 |  | 1515
7 | Expected amount in deposits | 1 |  |  | 1 | 1 |  | 100 | Done | 1 |  |  | 1 | 1 | 1 | 125
8 | BA new merchant PA | 5 | 5 |  |  |  |  | 275 | In process | 70 | 10 |  |  |  | 50 | 3300
9 | Freeze Merchant Drop Down in Wallet (only Front-end) | 2 |  |  |  | 1 |  | 85 | Done | 2 |  |  |  | 1 |  | 85
10 | Merchant Passthrough Fee | 3 | 1 |  |  |  |  | 105 | Posponed | 6 |  | 3 | 26 | 6 |  | 1550
11 | Investigate USDT over TON | 3 | 1 | 2 | 25 |  |  | 1205 | Done | 5 |  | 2 | 25 |  |  | 1225
[7 empty] | Subtotal | 15760 | [6 empty] | Total | 28820
Added tasks | [8 empty] | Status
12 | Small fixes 249) Add account id for deposit and payout creation tool and account id info to deposits, payouts and invoices pages. - done 735) Move and rename columns in CSV for deposits (“Amount of coins to transfer” should be renamed to “Expected amount” and placed to the left of “Coin”; “Address for transfer” should be renamed to “Deposit address” and placed to the left of “Hash”) - done 260) Change order of the USD and Coin in Base amount field in Swap table - done 751) Fix bch-17 wallet balance path - done 703) Delete incorrect using PositiveInt type from code -done 260) Reverse coin & USD values ​​in base amount field in Swaps table 263) Add refresh button to tools->wallets section | 2 |  |  | 21.5 | 2 |  | 980 | Done
13 | Сhange the order of the requests when we creating the wallet | 2 |  |  | 10 |  |  | 450 | Done
14 | Handle accumulation when `extend` was used | 1 |  |  | 14 |  |  | 585 | Done
16 | Fluctuating Coin and USD amount (Switch discord notifications about balance from USD to Coin) | 1 |  |  | 5 |  |  | 225 | Done
17 | Highload payout optimization_1 | 4 |  |  | 12 |  |  | 580 | Done
18 | Issue 508 (tools/actions/manual payout :: USDT/Tron transfer fails) | 4 |  |  | 2 |  |  | 180 | Done
19 | Add EVM BCs smart contract support | 3 |  | 2 | 35 |  |  | 1575 | In process (from sprint 30 )
20 | Sprint 28 fixes | 5 | 1 |  |  | 12 |  | 575 | Done
21 | BA tasks from backlog | 24 | 15 |  |  |  |  | 1050 | Done
[7 empty] | Subtotal | 6200
[7 empty] | Total | 21960
Note on F30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If it is exist in the system

## Sprint 30 (14.08 - 16.09) (hidden)
№ | Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) | 40 | 30 | 1200
2 | Max (PM) | 101.5 | 25 | 2537.5
3 | Kostya (Analytic) | 50 | 25 | 1250
4 | Philipp (Lead) | 24 | 50 | 1200
5 | Backend developer 1 | 228.5 | 40 | 9140
6 | Backend developer 2 | 200 | 40 | 8000
7 | Backend developer 3 | 45 | 40 | 1800
8 | Frontend developer 1 | 21.5 | 35 | 752.5
9 | Frontend developer 1 |  | 35 | 0
10 | Designer | 11.5 | 25 | 287.5
26167.5
|  | Actual | [6 empty] | Status | Estimation
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $ |  | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $
1 | REPORTS | [6 empty] | 0 | [7 empty] | 0
| Delete info about payouts from the Consolidator 's"totals" window |  |  |  |  | 1 |  | 35 | Done | 1 |  |  |  | 1 |  | 60
2 | Swap Confirmation | 2 |  |  | 2 |  |  | 130 | Done | 2 |  |  |  | 3 |  | 155
3 | Add EVM BCs smart contract support | 7 | 2 | 2 | 15 |  |  | 935 | Done | 16 | 2 | 6 | 54 |  |  | 2920
4 | Add an update button to the tools->wallets section | 0.5 |  |  |  | 0.5 |  | 30 | Done | 1 |  |  | 1 |  |  | 65
5 | Avalanche C BC (only coin) | 3 |  | 1 | 15 |  |  | 725 | Done | 2 |  | 1 | 12 |  |  | 580
6 | Avalanche X BC (only coin) | 3 |  | 1 | 52 |  |  | 2205 | Done | 10 | 3 | 5 | 44 |  |  | 2350
7 | Highload payout optimization_2 | 8 |  |  | 38 |  |  | 1720 | Done | [6 empty] | 0
8 | Cordano BC (only coin) | 4 |  | 1 | 50 |  |  | 2150 | Done | 9 | 2 | 5 | 44 |  |  | 2295
9 | Add Multiple choice to the filters | 4 |  |  | 19 | 8 | 1 | 1165 | Done | 6 | 2 | 2 | 12 | 8 |  | 1070
10 | Graylog Distiguish Long Term records from Short Term | [6 empty] | 0 | Posponed | [6 empty] | 0
11 | The settings section | 1 |  |  |  | 2 |  | 95 | Done | 2 |  |  |  | 4 |  | 190
12 | Show offchain deposits/payouts in reports | 6 | 1 | 1 | 22 | 4 |  | 1250 | Done | 6 | 1 | 3 | 24 | 6 |  | 1500
13 | Update logs for deposits with replace info | 4 |  |  | 3 | 1 |  | 255 | Done | 4 | 1 | 1 | 6 | 2 |  | 490
14 | Prohibit to change accumulator address in wallet's settings | 1 |  |  |  | 2 |  | 95 | Done | 2 | 1 |  |  | 1 |  | 115
15 | Search by address on accumulation page | 1 |  |  | 7 | 1 |  | 340 | Done | 1 |  | 1 | 6 | 2 |  | 385
16 | Add human-readable API error description | 23 |  | 1 | 15 |  |  | 1225 | Done | [6 empty] | 0
17 | Merchant Passthrough Fee | 8 | 1 | 2 | 34 | 1 |  | 1725 | Done | 6 |  | 3 | 26 | 6 |  | 1550
18 | Add USDT over TON | 10 | 2 | 2 | 45 |  |  | 2210 | Done | 12 |  | 8 | 75 |  |  | 3700
19 | Design an architecture: divide architecture of the BPS into 2 part - for merchant functions, for BC functions. |  | 5 | 9 | 40 |  |  | 2200 | Done |  | 5 | 5 | 20 |  |  | 1200
20 | BA tasks from backlog | 32 | 24 |  |  |  |  | 1520 | Done | 40 | 40 |  |  |  |  | 2200
[7 empty] | Subtotal | 20010 | [6 empty] | Total | 20825
Added tasks | [8 empty] | Status
21 | L2 Base | 2 |  | 2 | 38 |  |  | 1670 | Done
22 | BA new merchant PA | 15 | 5 |  |  |  | 10.5 | 787.5 | In Process
23 | Small fixes: 773 fix error description unknown server error and parse all proper descriptions 250 fix submit button 789 show proper creator in TX logs 274 Order of the reports became [Deposits, Payouts, ..., Deposit control, Payout control, Running balance]. Buttons order became [logs, details] 802 Duplication error 789 Correction of user information in transaction logs | 4 |  |  | 9 | 1 |  | 495 | Done
24 | Technical stuff 784 sometimes there are no logs if any service is down 771 some ETH payouts have mempool status forever 752 transaction idempotence for blockchain-service 764 delete ethgasstation 768-770 BNB payouts have stucked 785 accumulation errors with ETH-like transactions 790 `insufficient_balance` error of polygon accumulations 801 Wrong recipient of the Payout transaction 799 Unable to create USDT wallet | 4 |  | 1 | 19.5 |  |  | 930 | Done
25 | On restart of ETH nodes several container restarted | 1 |  |  | 6 |  |  | 265 | Done
26 | Fix enable/disable user function | 1 |  |  | 2 |  |  | 105 | Done
27 | Upgrade force feature when Gas Station down | 1 |  |  | 5 |  |  | 225 | Done
28 | The accumulation is deleted for any fail reasons | 1 |  |  | 7 |  |  | 305 | Done
29 | EVM bump fee for ETH, MATIC, AVAX C, etc.. | 3 |  | 1 | 20 |  |  | 925 | Done
30 | Send notification to Discord of Errored Deposit attempts | 2 |  |  | 10 |  |  | 450 | In process (Sentry)
[7 empty] | Subtotal | 6157.5
[7 empty] | Total | 26167.5

## Sprint 31 (17.09 - 11.11) (hidden)
№ | Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) | 61.75 | 30 | 1852.5
2 | Max (PM) | 154 | 25 | 3850
3 | Kostya (Analytic) | 26 | 25 | 650
4 | Philipp (Lead) | 40 | 50 | 2000
5 | Backend developer 1 | 274 | 40 | 10960
6 | Backend developer 2 | 304 | 40 | 12160
7 | Frontend developer 1 | 46.5 | 35 | 1627.5
8 | Frontend developer 1 |  | 35 | 0
9 | Designer | 60 | 25 | 1500
34600
|  | Actual | [6 empty] | Status | Estimation
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Actual price, $ |  | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $
1 | E-BPShop. Back-end: | 20 | 10 | 8 |  |  |  | 1200 |  | 20 | 10 | 30 |  |  |  | 2300
2024-01-01 | Create a monorepo |  |  |  | 30 |  |  | 1200 | Done |  |  |  | 30 |  |  | 1200
2024-02-01 | Create a nestjs skeleton |  |  |  | 9 |  |  | 360 | Done |  |  |  | 12 |  |  | 480
2024-03-01 | Configure PostgreSQL and connect to NestJS |  |  |  | 5 |  |  | 200 | Done |  |  |  | 4 |  |  | 160
2024-04-01 | User Auth(Z) + sign Up |  |  |  | 27 | 3 |  | 1185 | Done |  |  |  | 24 |  |  | 960
2024-05-01 | Create a Store entity and BL |  |  |  | 15 | 3 |  | 705 | Done |  |  |  | 16 |  |  | 640
2024-06-01 | User role in the store (interface of users and stores) |  |  |  | 13 |  |  | 520 | Done |  |  |  | 16 |  |  | 640
2024-07-01 | Connect the store with BPS merch (BPS REST) |  |  |  | 17 | 7 |  | 925 | Done |  |  |  | 28 |  |  | 1120
2024-08-01 | Implement CRUD for products |  |  |  | 8 | 5 |  | 495 | Done |  |  |  | 16 |  |  | 640
2024-09-01 | Create a payment link Payment session system |  |  |  | 15 |  |  | 600 | Done |  |  |  | 20 |  |  | 800
2024-10-01 | Autotests |  |  |  | 30 |  |  | 1200 | Done |  |  |  | 20 |  |  | 800
2024-11-01 | Deploy |  |  |  | 10 |  |  | 400 | Done |  |  |  | 16 |  |  | 640
2 | E-BPShop. Front-end: | 10 | 2 | 1 |  |  |  | 360 |  | 30 | 10 | 15 |  |  |  | 1800
2024-01-02 | Intiate repo, components |  |  |  |  | 3 |  | 105 | In process |  |  |  |  | 8 |  | 280
2024-02-02 | Auth+sign Up |  |  |  |  | 4.5 |  | 157.5 | In process |  |  |  |  | 14 |  | 490
2024-03-02 | Settings-Buisiness details | [6 empty] | 0 | Posponed |  |  |  |  | 26 |  | 910
2024-04-02 | Balances | [6 empty] | 0 | Posponed |  |  |  |  | 24 |  | 840
2024-05-02 | Payment links (table, creation) | [6 empty] | 0 | Posponed |  |  |  |  | 48 |  | 1680
2024-06-02 | Products (table, creation) | [6 empty] | 0 | Posponed |  |  |  |  | 40 |  | 1400
3 | E-BPShop. Analitics, design | 80 | 29 | 8 |  |  | 60 | 4770 | Done | 120 | 40 | 8 |  |  | 100 | 7100
4 | BC Optimism | 4 |  | 1 | 16 |  |  | 790 | Done | 4 |  | 2 | 24 |  |  | 1160
5 | BC Arbitrum | 4 |  | 1 | 16 |  |  | 790 | Done | 4 |  | 2 | 24 |  |  | 1160
6 | BA: General Hot Wallet | [6 empty] | 0 |  | 20 | 10 |  | 8 | 50 |  | 2870
7 | Redesign Force feature for EVM with changing Max NF from coin to Wei | 8 |  | 2 | 16 | 12 |  | 1360 | Done | 2 |  |  | 12 | 10 |  | 880
8 | Graylog Distiguish Long Term records from Short Term |  |  | 0.5 | 3 |  |  | 145 | Done |  |  | 2 |  | 12 |  | 520
9 | Add button to redirect to ".../version" window | 1 |  |  |  | 1 |  | 60 | Done | 1 |  |  | 3 | 1 |  | 180
10 | Add USDT over TON | 6 |  | 1 | 16 |  |  | 840 | Done | 6 |  | 2 | 10 |  |  | 650
11 | Configure Sentry |  |  | 1 | 18 |  |  | 770 | Done |  |  |  | 20 |  |  | 800
12 | BA tasks from backlog | 30 | [5 empty] | 750 | Done | 30 | 30 |  |  |  |  | 1650
[7 empty] | Subtotal | 19887.5 | [6 empty] | Subtotal | 34750
[15 empty] | Without posponed tasks | 27050
Added tasks
13 | Optimization of confirmed transaction search for blockchain scanners The system often threw an error on the number of connections to the database. We investigated what could be connected with it, and looked for ways to fix it. We came to the optimization of the number of requests to the database - we rewrote part of the code for searching in the scanners of transactions that relate to the addresses of our system. |  | 9 | 6 | 25 |  |  | 1570
14 | Optimization of new transaction search for Bitcoin We determined the methods for obtaining the bitcoin mempool, since in that state the system within the scanner could not receive the mempool in its entirety. At first, we wanted to use mempool.space (the code was already ready), but eventually switched to bitcoin core. For the mempool, we also optimized the search for transactions for our addresses. After writing the scanners, we dealt with the very low scanning speed. We made a number of optimizations. |  | 6.75 | 4.5 | 52 |  |  | 2507.5
15 | New model BTC scanner We investigated the problem when bitcoin-like transactions were lost. Then we found that the node cannot give more than a certain number of transactions to one address. There were also many discussions on the topic of changing the model for receiving transactions in bitcoin-like ones, where we eventually came to scanners. We implemented them, but during development some difficulties arose due to the specifics of the BC. |  |  |  | 43 |  |  | 1720
16 | Creating business metrics | 4 |  |  | 16 |  |  | 740
17 | Investigating difference between WPB and BPS deposits We have investigated 3 times within the sprint differences between two system, the cases of differences were: 1. BPS had been restarting and WPB hadn't able to send deposit address 2. New ETH-like (also USDT) SCs which weren't supported at that moment 3. Uncommon deposits with no hash / incorrect data (i.e. created for ETH but replenished in BASE) 4. Missed deposit wallet (i.e WPB have started send to us AVAX-C but wallet wasn't created) | 2 |  |  | 16 |  |  | 690
18 | TRON issues In task #847 we have found addresses in raw format. It have fixed. In #862 we have fixed missing error if there is unsufficient balance In #863 we have fixed out-of-sync account on the production server. | 4 | 3 | 2 | 24 |  |  | 1250
19 | BC worker freezes #837 - BC-worker is not reload after the error #839 - Fix BC-worker freezes #850 - Freezes within stress testing #868 - BPS received uncommon SC TXs which have replenished 2 deposits | 2 | 2 | 2 | 56 |  |  | 2450
20 | EBPS Backend
2024-01-20 | Swagger |  |  |  | 6 |  |  | 240
2024-02-20 | Internal logs (debug) |  |  |  | 4 |  |  | 160
21 | Preparation for e2e: semi-automatic script for payouts | 2 |  |  | 8 |  |  | 370
22 | Fix potential vulnerability: correct process blank and failed ETH TXs |  |  |  | 16 |  |  | 640
23 | Add cardano legacy addresses support with fix memory loses | 1 |  |  | 12 | 4 |  | 645
24 | Small fixes #840 Accidentally accumulation is in payout table instead of the proper one #833 No data at wallets page #842 Two identical pending payouts #276 Fix incorrect namings #849 save every TRX TXs #854 add new SCs to support #865 Incorrecy logs of updated balance #855 Replace func doesn't work in ETH-like BCs (tokens) #859 Blockscout gas tracker doesn't work from 11th October #860 Add support for SC executeCallWithData #867 Errored accounting of the used deposit' addresses #874 Transaction has been reverted by the EVM #283 Unable to create hot deposit/general wallet for tokens #881 gas required exceeds allowance (21000) for arbitrum | 2 |  | 1 | 16 | 4 |  | 880
25 | Technical stuff #797 AVAX-C scanner sometimes doesn't work #823 Fix CI #864 move fixes in master branch #877 Fix logs and fix in admin service #857 Fix the 502 errors (socket hang up) #841 avax proxy |  |  | 1 | 20 |  |  | 850
[7 empty] | Subtotal | 14712.5
[7 empty] | Total | 34600

## Sprint 32 (12.11 - 23.12) (hidden)
№ | Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) | 30 | 30 | 900
2 | Max (PM) | 194 | 25 | 4850
3 | Kostya (Analytic) | 30 | 25 | 750
4 | Philipp (Lead) | 25 | 50 | 1250
5 | Backend developer 1 | 190 | 40 | 7600
6 | Backend developer 2 | 158.25 | 40 | 6330
7 | Frontend developer 1 | 150 | 35 | 5250
8 | Frontend developer 1 | 46 | 35 | 1610
9 | Designer | 26 | 25 | 650
29190
Actual | [8 empty] | Status | Estimation
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Actual price, $ |  | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $
1 | E-BPShop feauters | 39 | 6 | 4 |  |  |  | 1355 |  | 40 | 10 | 15 |  |  |  | 2050
1.1 | Components |  |  |  |  | 30 |  | 1050 | Done |  |  |  |  | 5 |  | 175
1.2 | Auth Sign in |  |  |  | 2 | 20 |  | 780 | Done |  |  |  |  | 14 |  | 490
1.3 | Settings-Buisiness details | [6 empty] | 0 | Posponed |  |  |  |  | 26 |  | 910
1.4 | Balances |  |  |  | 6 | 24 |  | 1080 | Done |  |  |  |  | 24 |  | 840
1.5 | Products |  |  |  | 24 | 35 |  | 2185 | Done | [6 empty] | 0
1.6 | Payment links Payment session |  |  |  | 36 | 41 |  | 2875 | Done | [6 empty] | 0
2 | E-BPShop. Back-end: | [6 empty] | 0 | Done | [6 empty] | 0
| Deployment |  |  | 2 | 16 |  |  | 740 | Done |  |  |  | 16 |  |  | 640
3 | E-BPShop. Analitics, design | 75 | 15 | 3 |  |  | 26 | 3125 | Done | 100 | 20 | 8 |  |  | 40 | 4500
4 | BA tasks from backlog | 21 | [5 empty] | 525 | Done | 30 | 5 |  |  |  |  | 900
5 | Solving serialization issue | [6 empty] | 0 | Posponed |  |  | 5 | 60 |  |  | 2650
6 | Extended Transaction does not update Dashboard | [6 empty] | 0 | Replaced by 7 | 1 |  |  | 1 | 1 |  | 100
7 | Change filtration with the "confirmed at" datetime on the Deposits and Dashboard pages | 2 |  |  |  | 10 |  | 400 | Done | [6 empty] | 0
8 | Add processing SC TXs ETH using debug API (ex Manual process unknown SCs: pending deposits) | 16 | 4 | 6 | 35 |  |  | 2220 | Done | 16 | 5 | 5 | 40 | 12 | 8 | 3020
9 | Upgrade Bump TXs ETH-like | 15 |  |  | 15 | 2 |  | 1045 | Done | 8 |  |  | 16 | 8 |  | 1120
10 | Upgrade Bump TXs BTC (cpfp) | 8 |  | 2 | 32 | 4 |  | 1720 | Done | 8 |  |  | 40 | 8 |  | 2080
11 | Upgrade Download CSV | 5 |  |  | 11.5 | 7 |  | 830 | Done | 6 |  |  | 6 | 6 |  | 600
12 | Wallet's, merchant's and balance's pages optimization initial research | 4 |  |  | 10.75 |  |  | 530 | Done | 4 |  |  | 16 |  |  | 740
13 | Research for necessity of Blockscanner for AVAX-X | 3 |  |  | 7 |  |  | 355 | Done | 4 |  |  | 12 |  |  | 580
14 | Designing horizontal scaling for BC-scanners |  |  | 5 | 8 |  |  | 570 | Done |  |  | 4 | 20 |  |  | 1000
15 | Add new time column - Reports / Payouts pages | 1 |  |  | 7 |  |  | 305 | Done | 1 |  |  | 2 | 4 |  | 245
16 | New logs for payouts (cold pending, force, retry, decline, accept) | 3 |  |  | 6 |  |  | 315 | Done | 4 |  |  | 1 | 3 |  | 245
[7 empty] | Subtotal | 22005 | [6 empty] | Subtotal | 22885
[15 empty] | Without posponed tasks | 19325
Added tasks
17 | Polygon Native Coin name change |  | 1 | 2 | 2 |  |  | 210
18 | Add hook when node have 400s and 500s response codes | 4 |  | 1 | 16 |  |  | 790
19 | Unique TraceID for payouts | 8 | 4 |  | 8 | 6 |  | 850
20 | Pending Missing Info (add info to the Pending/ Failed pages - amount in USD, Exchange rate) | 1 |  |  |  | 2 |  | 95
21 | Update Deposit Report (tooltip should display the USD amount when hovering over the following elements: Merchant Fee, Consolidation Fee) | 1 |  |  |  | 4 |  | 165
22 | Code modification for full support AVAX-X |  |  |  | 2.5 |  |  | 100
23 | BTC and LTC transactions on Mempool state but not Completed: - investigated TXs itself and statement in blockchain - researching reasons for stucked in mempool - creating SQL-requests for fixing mempool statuses - developing fix for scenario with addresses in upper-case | 8 |  |  | 15 |  |  | 800
24 | 897 Tron Fix: exceed API requests - Fixed stucked old TX which used half of the limit - Changed TronGrid api-key |  |  |  | 5 |  |  | 200
25 | 299 Force window for L1 ETH-like (BNB, POLY, AVAX) 901 Add Gas Trackers for L1 ETH-like - Necessary for correct behaviour of new force window |  |  |  | 10 |  |  | 400
26 | 298 Error filtering pages payouts / accumulations - solving AVAX issue, how it works with date-time |  |  |  |  | 5 |  | 175
27 | 292 Collapse addresses in deposit info window |  |  |  |  | 1 |  | 35
28 | 887 Modification TON logic - Add processing address deployment - Fix request caching which returns incorrect value - Fix rate for token in force window |  |  |  | 12 |  |  | 480
29 | 902 Incorrect proceed using replace function on TON 890 Fix replace from native coin to the token |  |  |  | 12 |  |  | 480
30 | 833 Wallets returns no data - requests optimisation, solving timeout issue - Stage server faced with error `No results found` with no reason in time requesting Wallets data - Investigated SQL-requests - Reworked index in request - Switch from 4 req/wallet to one general request |  |  |  | 12.5 |  |  | 500
31 | 889 BigDecimal support in API |  |  |  | 5 |  |  | 200
32 | Small fixes 293 Hide "address from" 291 Change the logic of chosen filter via redirect from tools->actions:create swap 289 Edits in force 296 Fix rates in force window 916 Payouts downloading CSVs also take accumulations 915 Converting bitcoin and litecoin addresses to standard form ignores case in P2WPKH addresses | 5 |  |  | 16 | 4 |  | 905
33 | Technical stuff 913 Updated nodes, fix incorrect links 918 WalletNotFoundError with existing wallet 888 discrepancy in balances for TON in case of wallet's deployment 899 Fix broken download payouts CSV 886 Fix failed accumulation with unknown error 911 SyntaxError in graphQL 923 Incorrect data from PolygonScan gas tracker | 5 |  |  | 16 | 1 |  | 800
[7 empty] | Subtotal | 7185
[7 empty] | Total | 29190

## Sprint 33 (24.12 - 10.02) (hidden)
№ | Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) | 32.5 | 30 | 975
2 | Max (PM) | 207.5 | 25 | 5187.5
3 | Kostya (Analytic) | 29 | 25 | 725
4 | Philipp (Lead) | 30 | 50 | 1500
5 | Backend developer 1 | 183 | 40 | 7320
6 | Backend developer 2 | 185 | 40 | 7400
7 | Backend developer 3 | 6 | 40 | 240
8 | Frontend developer 1 | 225 | 35 | 7875
9 | Frontend developer 2 | 34.5 | 35 | 1207.5
10 | Designer | 36.3 | 25 | 907.5
33337.5
|  | Actual | [6 empty] | Status | Estimation
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Actual price, $ |  | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $
| E-BPShop: | 46 | 8 | 6 |  |  |  | 1690 |  | 60 | 5 | 8 |  |  |  | 2050
1 | BPS payment links Payment session modification + optimization |  |  |  | 24.5 | 13.5 |  | 1452.5 | done |  |  |  | 32 | 6 |  | 1490
2 | Front-end optimization, improvement - Width adaptive - Width limit for table - Backend pagination for products & invoices - Frontend pagination for balances - Numeric input field with +/- buttons for products. - "Create new" button for product selection during payment link creation. - Change toast notifications to match design. - Implement right-click to open pages in new tabs. - Fix status badges. - Create a custom currency conversion component. - Add scroll functionality to the side menu. - Implement a page header fixed to the top of the screen with a settings button. - Add `Enter` key support for: - System login after filling all inputs - New user creation |  |  |  |  | 38 |  | 1330 | done |  |  |  |  | 28 |  | 980
3 | Withdraw (page+action) |  |  |  | 24 | 29 |  | 1975 | done |  |  |  | 16 | 38 |  | 1970
4 | Deposits (page+action) |  |  |  | 12 | 16 |  | 1040 | done |  |  |  | 6 | 24 |  | 1080
5 | Auto creation merch in BPS | [6 empty] | 0 | replaced by 6 |  |  |  | 28 |  |  | 1120
6 | Semi-automatic merchant creation in BPS - semi-automatic merch confirmation itself in BPS - full-weight UI for admins - `pending merchants` BPS frontend - ability for requesting confirmation from E-BPS - secured endpoint for exact purposes - logic of work between systems |  |  |  | 78 | 29.5 |  | 4152.5 | done
7 | BPS Callbacks modification |  |  |  | 16 |  |  | 640 | done |  |  |  | 16 |  |  | 640
8 | Invoices (page + action) |  |  |  | 7 | 30 |  | 1330 | done |  |  |  | 24 | 38 |  | 2290
9 | Settings -> Business details |  |  |  |  | 18 |  | 630 | done |  |  |  | 4 | 20 |  | 860
10 | E-BPShop. Analitics, design | 55 | 6 | 4 |  |  | 36.3 | 2662.5 | done | 60 | 16 | 3 |  |  | 40 | 3130
| E-BPShop: Deployment | [6 empty] | 0 | [7 empty] | 0
11 | ci/cd, observability, deployment (tech analyze) |  |  | 1 | 6 |  |  | 290 | done |  |  | 1 | 4 |  |  | 210
12 | ci/cd, observability, deployment | [6 empty] | 0 | postponed | [6 empty] | 0
| BPS | [6 empty] | 0 | [7 empty] | 0
| Autotests | [6 empty] | 0 | [7 empty] | 0
14 | acceptance tests | 24 | 4 | 5 | 39 |  |  | 2530 | done | 24 |  | 4 | 40 |  |  | 2400
15 | Optimization merchant & balance pages | 6 |  |  | 16 |  |  | 790 | done | 4 |  |  | 16 | 2 |  | 810
16 | Lowest value definition for accepting deposit | 6 |  |  | 8.5 |  |  | 490 | done |  |  |  | 8 |  |  | 320
17 | MAU-20: [BA] Frontend dashboard updates​ | 12 | 1 |  | 3 |  |  | 450 | done | 16 | 4 | 1 |  |  |  | 570
18 | Extend API validation | 2 |  |  | 1 |  |  | 90 | done |  |  |  | 8 |  |  | 320
19 | Solving serialization issue | 4 |  | 1.5 | 14 |  |  | 735 | done | 8 |  | 5 | 60 |  |  | 2850
20 | [BA] Utila | 24 | 4 | 2 |  |  |  | 820 | done | 30 | 10 | 5 | 4 |  |  | 1460
21 | [Tech analyze] Relay: sweep tokens without coins | 6 | 0.5 | 4 | 7 |  |  | 645 | done | 2 |  | 2 | 4 |  |  | 310
| Technical stuff | [6 empty] | 0 | contains tasks 22-29 |  |  |  | 12 | 12 |  | 900
22 | 939 Services restarting w/o errors - fix gRPC amount of active connections which uses a lot RAM | 0.5 |  | 1 | 8 |  |  | 382.5 | done | [5 empty] | Total | 25760
23 | 938 Deadlock in execution moveScannerTransactionsToAccountTransactions - solved deadlock issue in `accounts` requests | 0.5 |  | 1 | 10 |  |  | 462.5 | done | [5 empty] | Without postponed tasks | 25760
24 | 925 REST API tests fell |  |  |  | 1 |  |  | 40 | done
25 | 295 Transition from to and from toAddress and fromAddress for graphql type TransferRequest - optimize loading pages using field with dataloaders |  |  |  |  | 6 |  | 210 | done
26 | 950 Optimize slow request of raw transactions from the blockchain |  |  |  | 3 |  |  | 120 | done
27 | 926 Script for deposits stress testing - extended script for stress testing |  |  |  | 2.5 |  |  | 100 | done
28 | 927 Freezes ETH scanner within SC processing - change grouping method | 1 |  | 0.5 | 5 |  |  | 250 | done
29 | 918 WalletNotFoundError when system have existing wallet - double deposit requests from WPB | 2 |  |  | 1.5 |  |  | 110 | done
[7 empty] | Subtotal | 25417.5
Added tasks
E-BPShop:
30 | Account details | 8 | 2 |  | 7 | 21 |  | 1275 | done
31 | Small fixes & tech - 69 Fix layout, change 2fa naming, fixerror, fix pdf - 67 Auto avoid decline from BPS, fix lost fields in API - 74 refresh token rework - 11 Investigate and optimize invoice (PS) loading - 66 Fix front->back incorrect requests | 11 | 2 |  | 20 | 6 |  | 1345 | done
32 | Custom multiselector for currencies | 2 |  |  |  | 8 |  | 330 | done
33 | Loaders: - loading state for buttons - `loading` component - animated loader with logo | 1 |  |  |  | 5 |  | 200 | done
34 | DB migrations |  |  | 1 | 11 |  |  | 490 | done
35 | Emails (signUp/In, recovery password) | 2 | 1 | 1 | 13 | 11 |  | 1035 | done
| BPS | [6 empty] | 0 | done
35 | 150 Pending missing info 2 (approved 01.30.2025) - added coin and fee amounts in `pending` pop-up menu | 1 |  |  |  | 6.5 |  | 252.5 | done
36 | 158 Rework Unique TraceIDs | 4 | 2 |  | 9 |  |  | 520 | done
37 | 310 Additions for force window | 4 | 1 | 0.5 |  | 7 |  | 400 | done
38 | 312 Bringing the force to the relevant token rate | 4 | 1 | 0.5 |  | 6 |  | 365 | done
39 | 924 Replace expired deposits | 1 |  |  | 1 |  |  | 65 | done
40 | 929 Add validation for coin_amount with null/string | 0.5 |  |  | 4 |  |  | 172.5 | done
41 | 954 Out-of-sync ETH FMT node - investigate the reasons of out-of-sync - fix arbitrum alerts which have interfere to understand the situation | 1 |  |  | 4 |  |  | 185 | done
42 | 934 Process stake TRX TXs -Transfer TRX - basic TRX transfer; - Trigger Smart Contracts - transfer TRC20 tron token, supported until now; - Transfer TRC10 - added support as it can affect balance due to fees; - TRX Stake (2.0) - added support - “freezes” some funds that are no longer in the balance; - TRX Unstake (2.0) - added support due to commission. Does not affect balance directly. Transfers currency from stake to unstake, which is also unavailable for use; - Cancel Unstake - added support due to commission. Transfers currency from unstake back to stake; - Withdraw Unstaked TRX - added support - unfreezes funds from unstake and returns them to the balance; - Delegate Resources - added support due to commission. Balance is not affected. - Reclaim Resources - added support due to commission. Balance is not affected. - TRX Stake (1.0) - not supported by node. - TRX Unstake (1.0) - added support - “unfreezes” stake v1 funds. - Vote - added support due to commission. Balance is not affected. - Claim Voting Rewards - added support - receiving rewards in TRX. - Update Account Permissions - added support due to commission | 2.5 |  | 1 | 10 |  |  | 512.5 | done
Small Fixes
43 | 309 Fix column headings in tables | 1 |  |  |  | 9 |  | 340 | done
44 | 308 Remove ability for creating payout HD-wallet | 1 |  |  | 0.5 |  |  | 45 | done
45 | 936 Fix searching using uuid in payouts/accumulations | 0.5 |  |  | 0.5 |  |  | 32.5 | done
46 | 951 Update TON API spec | 2 |  |  | 2 |  |  | 130 | done
47 | 962 Add logs for TON TXs | 1 |  |  | 5 |  |  | 225 | done
[7 empty] | Subtotal | 7920
[7 empty] | Total | 33337.5

## Sprint 34 (11.02-15.05) (hidden)
№ | Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) | 21.5 | 30 | 645
2 | Max (PM) | 324.5 | 25 | 8112.5
3 | Kostya (Analytic) | 7 | 25 | 175
4 | Philipp (Lead) | 24 | 50 | 1200
5 | Backend developer 1 | 98 | 40 | 3920
6 | Backend developer 2 | 327 | 40 | 13080
7 | Frontend developer 1 | 51.5 | 35 | 1802.5
8 | Frontend developer 1 |  | 35 | 0
9 | Designer |  | 25 | 0
28935
|  | Actual | [6 empty] | Status | Estimation
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Actual price, $ |  | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $
1900-01-01 | BPS | [6 empty] | 0 | done | [6 empty] | 0
2025-01-02 | Solana (coin + tokens (memes)) | 16 | 1 | 1 | 44.5 |  |  | 2260 | done | 16 | 1 | 1 | 52 |  |  | 2560
2025-02-02 | Ripple | [6 empty] | 0 | done | 12 | 1 | 1 | 48 |  |  | 2300
- | Full func. | 12 | 1 | 1.5 | 40.5 |  |  | 2025 | done
- | Hot deposit wallet XRP can not be created | 1 |  |  | 1 |  |  | 65 | done
2025-03-02 | XLM | 12 |  | 1.5 | 46.5 |  |  | 2235 | done | 12 | 1 | 1 | 48 |  |  | 2300
2025-04-02 | DOGE | [6 empty] | 0 | done | 12 | 1 | 1 | 12 |  |  | 860
- | Full func. doge - was designed to be completely consistent with Bitcoin logic, as was the case for l1 Ethereum-like coins. In the process, several significant differences were found (we had to write a separate parser for hex blocks and hex transactions). Also, there was basically no regtest node for e2e tests, so we had to make our own based on electrumx. During testing on real nodes, we had to make adjustments to support these very real nodes. | 11.5 | 1 | 1 | 19.5 |  |  | 1147.5 | done
- | An error occurs when creating a doge hot payout wallet Related to the incorrect connection with the node - DOGE node was unstable with connection | 1 |  |  | 3 |  |  | 145 | done
- | Change reconnect trigger for WS client For DOGE node code changes of connection to gain full-time connection with it |  |  |  | 4 |  |  | 160 | done
- | Ping in electrum client does not start until some request is executed | 1 |  |  | 2 |  |  | 105 | done
2025-05-02 | Acceptance tests | [6 empty] | 0 | done | [6 empty] | 0
- | Local deployment of bitcoin-like BC nodes | 2 | 2 |  | 14 |  |  | 670 | done | 2 | 2 |  | 20 |  |  | 910
- | `Actions` implementation in acceptance flow for Bitcoin-like BC According to the tests, the initial stage of preparing the Testnet nodes took a long time, as each node had its own characteristics. Their fine-tuning took place throughout the entire task execution period. | 24 | 2 | 2.5 | 50 |  |  | 2785 | done | 2 | 2 | 2 | 32 |  |  | 1490
2025-06-02 | Relay: | [6 empty] | 0 | cancelled | [6 empty] | 0
- | sponseredCall | [6 empty] | 0 | [7 empty] | 0
- | callWithSyncFee | [6 empty] | 0 | [7 empty] | 0
2025-07-02 | [Tech analyze] Utila | 15 | 1 | 2 |  |  |  | 505 | cancelled | 12 |  |  | 0 |  |  | 300
2025-08-02 | MATIC -> POLY (manually deleted MATIC from DB) | 1.5 |  | 1 | 10 |  |  | 487.5 | done |  |  |  | 12 |  |  | 480
2025-09-02 | Failed Accumulation cannot be deleted Changes to the backend: - Renamed the variable `DEFAULT_LIMIT` to `DEFAULT_LIMIT_QUERY` in the `bookkeeper` service and made it publicly available in the service - `get-action-by-ids` works correctly (pulling up `pending` and `failed` actions) - the sequence of requests and their correct operation have been fixed - All new functionality is covered by tests Frontend changes: - `Decline` has appeared in accumulations - When selecting different currencies in stacked tables, the amount in USD is displayed correctly - incorrect USD calculation has been fixed |  |  | 0.5 |  | 12 |  | 445 | done | 4 |  |  | 4 | 1 |  | 295
2025-10-02 | [BA] new merchant acc | [6 empty] | 0 | done | 32 | 6 |  |  |  |  | 980
- | [MAU-209] Wallets improvment | 6.5 | [5 empty] | 162.5 | done
- | Rework access rights | 3 | [5 empty] | 75 | done
- | Admin quorum | 20.5 | 2 |  |  |  |  | 572.5 | done
- | EVM wallets | 31 | 2 | 0.5 |  |  |  | 860 | done
- | Delegate wallet | 21 | 2 |  |  |  |  | 585 | done
- | Sponsor wallet + EIP-3009 \ EIP-7702 | 15 | 2 | 1 |  |  |  | 485 | done
- | Bitcoin based Network Batching Wallet for deposits | 8 | 0.5 |  |  |  |  | 215 | done
- | Rework extend | 11 | 0.5 |  |  |  |  | 290 | done
- | Delete old records from outbox table | 5 | [5 empty] | 125 | done
- | Horizontal scaling | 4 | [5 empty] | 100 | done
- | Divide worker processes in the blockchain service | 2.5 | [5 empty] | 62.5 | done
- | [MAU-226] Operator issue | 2.5 | 0.5 |  |  |  |  | 77.5 | done
- | [General] Rethink process of current workflow | 7 | 1 |  |  |  |  | 205 | done
- | Add @ tags for hooks in discord for out-of-sync nodes | 1.5 | [5 empty] | 37.5 | done
2025-11-02 | Technical stuff | [6 empty] | 0 | done |  |  |  | 15 | 15 |  | 1125
- | application error when click on the details (reports->deposit control)) | 0.5 |  |  |  | 1.5 |  | 65 | done
- | extend doesn't work | 0.5 |  |  |  | 1 |  | 47.5 | done
- | merchant `cannot execute use on page_filter` | 1 |  |  |  | 2.5 |  | 112.5 | done
- | Operator, Accountant Permission denied | 1 |  |  |  | 2.5 |  | 112.5 | done
- | version `could not fetch` error | 0.5 |  |  |  | 1.5 |  | 65 | done
- | Incorrect maxfee fee for SHIBs | 1 |  |  |  | 4 |  | 165 | done
- | Fix coin and token rates on the front end | 0.5 | 0.5 |  |  | 5 |  | 202.5 | done
- | Broken modals (deposit info, payout info) | 0.5 |  |  |  | 1.5 |  | 65 | done
- | Remove sorce_types_N in blockchain block sync dashboard in Graphana | 0.5 |  |  | 0.5 |  |  | 32.5 | done
- | Timeout errors in `blockchain service` autotests in runner | 0.5 |  |  | 1.5 |  |  | 72.5 | done
- | Blocks in scanner may not be deleted | 0 |  |  | 4 |  |  | 160 | done
2025-12-02 | Add CoinGecko rate provider and adapt it for ETH-SHIB rate - possible use that rate for future - currently will be used for ETH-SHIB rate (13.03 over sprint) | 6.5 | 1 |  | 21 |  |  | 1032.5 | done | 4 | 2 | 4 | 36 |  |  | 1800
2.13 | Adapt RETH ETH node for work with BPS (13.03 over sprint) | 2 | [5 empty] | 50 | postponed | 4 |  |  | 8 |  |  | 420
2.14 | [TA] Investigate how to reduce minimal costs of fee sending BTC-like TXs (13.03 over sprint) | 0.5 |  |  | 11 |  |  | 452.5 | done | 1 |  |  | 12 |  |  | 505
2.15 | Frontend optimization for Deposits, Payouts, Accumulation, etc. - edits for GraphQL requests & optimization frontend logic - add dataloaders on the backend (13.03 over sprint) Includes studying the logic of operation and data loading for pages. Changed: - Instead of calculations on the back end, the front end now calculates values in dollars. - Unnecessary `blockTransactions` requests have been removed. - The ability to round down in the `toUsd` function has been added. - Payment sessions are no longer requested in payments; they are now requested separately. - Unused values have been reviewed and deprecated. | 1 | 0.5 | 2 | 7 | 13.5 |  | 892.5 | done | 1 |  |  | 5 | 5 |  | 400
2.16 | Delayed batch-accumulation (20.03 over sprint) | 1 |  |  | 6 |  |  | 265 | done | 2 |  |  | 6 |  |  | 290
2.17 | Switch to the Fastify from Koa | [6 empty] | 0 | done |  |  |  | 24 |  |  | 960
- | Switch to Fastify Gained advantages: - Higher perfomance (look into task MAU-234) - Built-in schema validation - further API endpoints development will take less time | 2 |  | 2 | 22 |  |  | 1030 | done | [5 empty] | Without postponed tasks | 17015
2.18 | [MAU-185] Change the information in the swagger | 1 |  |  | 0.5 |  |  | 45 | done
2.19 | [MAU-203] Coin/token ticker | 0.5 |  |  |  | 5 |  | 187.5 | done
2.20 | Bring background processing of notifications and getting raids from grpc to wokers | 1 |  | 1 | 13.5 |  |  | 615 | done
2.21 | [MAU-253] Blackbox exporter: add instance names and gas trackers | 2.5 | 0.5 | 0.5 | 20 |  |  | 902.5 | done
2.23 | Testing | [6 empty] | 0 | done
- | Upgrade test-cases | 4 | [5 empty] | 100 | done
- | Regression testing | 32 | [5 empty] | 800 | done
[7 empty] | Subtotal | 24360
Added tasks
2.17 | Switch to the Fastify from Koa | [6 empty] | 0 | done
- | Switching API controllers to Fastify |  |  | 1 | 10 |  |  | 450 | done
- | Upgrade related `Koa` libraries to `Fastify` counterparts |  |  | 1 | 16 |  |  | 690 | done
2.24 | Use alpine-based nodejs image |  |  |  | 4 |  |  | 160 | done
2.25 | Short lived Jaeger traces |  |  |  |  | 1.5 |  | 52.5 | done
2.26 | Generate validation schema and types based on swaggerV2.yaml |  |  |  | 2 |  |  | 80 | done
2.27 | Add configuration parameters to enable blockchains |  |  |  | 1 |  |  | 40 | done
2.28 | Node optimism started giving wrong values of last block number | 1 |  |  | 2 |  |  | 105 | done
2.29 | ETH ws-node error | 1 |  |  | 2.5 |  |  | 125 | done
Technical help desk
2.31 | updating env in alphabetical order | 0.5 |  |  | 1 |  |  | 52.5 | done
2.32 | SQL queries to update accumulator address | 1 |  | 0.5 | 1.5 |  |  | 110 | done
2.33 | SQL queries to switch operator->consolidator | 0.5 |  |  | 0.5 |  |  | 32.5 | done
2.34 | Production slowdown after deposits are connected | 3 | 0.5 | 0.5 | 4 |  |  | 275 | done
2.35 | [MAU-185] Explore broken Blockfills | 2 |  |  | 3 |  |  | 170 | done
2.36 | [MAU-208] Add `tx_hash` to `deposit_callback` | 0.5 |  | 0.5 | 2 |  |  | 117.5 | done
2.37 | [MAU-213] Bump ether token returned error ‘Transaction too expensive. Make max fee smaller.’ | 3.5 |  |  | 8.5 |  |  | 427.5 | done
2.38 | Errors of deposit creation on prod (27.02) | 1 |  | 0.5 | 2 |  |  | 130 | done
2.39 | Tron transaction hangs unprocessed on staging | 1 |  | 0.5 | 3 |  |  | 170 | done
2.40 | Restart of blockchain service on proda 01.05 | 1.5 |  | 0.5 | 5.5 |  |  | 282.5 | done
2.41 | Invalid opcode error in USDT ETH payments | 2.5 |  | 1 | 10.5 |  |  | 532.5 | done
2.42 | Ether-like BC debug trace parser crashes when processing contract creation |  |  |  | 2 |  |  | 80 | done
2.43 | [MAU-214] Extending LTC TX with multioutput | 1 | [5 empty] | 25 | done
2.44 | [MAU-227] Duplicate Records investigation | 2 | [5 empty] | 50 | done
2.45 | MAU-197: These two transactions Failed | 3 | [5 empty] | 75 | done
2.46 | creating wallet LTC-31 on the Stage | 1 | [5 empty] | 25 | done
2.47 | Provider reconnect before any response | 2 | [5 empty] | 50 | done
2.48 | Sync AVAX-C & POL blocks in BPS DB | 3 |  |  | 1 |  |  | 115 | done
2.49 | Guides update | 3.5 | [5 empty] | 87.5 | done
2.50 | BTC-39 & BTC-40 wallets issue | 1 |  |  | 1 |  |  | 65 | done
[7 empty] | Subtotal | 4575
[7 empty] | Total | 28935

## Sprint 35 (19.05-19.06) (hidden)
№ | Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) | 11 | 30 | 330
2 | Max (PM) | 59 | 25 | 1475
3 | Kostya (Analytic) |  | 25 | 0
4 | Philipp (Lead) | 20 | 50 | 1000
5 | Backend developer 1 | 184.5 | 40 | 7380
6 | Backend developer 2 | 39 | 40 | 1560
7 | Backend developer 3 | 34 | 40 | 1360
8 | Frontend developer 1 |  | 35 | 0
9 | Frontend developer 1 |  | 35 | 0
10 | Designer |  | 25 | 0
13105
|  | Actual | [6 empty] | Status | Estimation
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Actual price, $ |  | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $
1 | Horizontal scaling | [14 empty] | 0
- | Generalization of the structure of scanner tables |  |  |  | 12.5 |  |  | 500 | done |  |  |  | 8 |  |  | 320
- | Splitting a worker into subservices |  |  | 1.5 | 23 |  |  | 995 | done |  |  | 3 | 30 |  |  | 1350
- | Blockchain provider services |  | 4 | 5 | 32 |  |  | 1650 | done |  | 5 | 5 | 45 |  |  | 2200
- | Transition of calls to nodes to calls to the API provider in the worker and API services |  | 3 | 5 | 38 |  |  | 1860 | done |  | 5 | 5 | 45 |  |  | 2200
- | Setting up new services for deployment in prod and dev environments |  |  | 2 | 23 |  |  | 1020 | done |  |  | 2 | 24 |  |  | 1060
2025-01-01 | DevOps (1) | [11 empty] | 25 |  |  | 1000
- | Local deployment |  |  |  | 7 |  |  | 280 | done
- | Technical designing |  |  | 3 | 17 |  |  | 830 | done
- | Ansible playbooks for managing the cluster |  |  | 0.5 | 8 |  |  | 345 | done
- | Switch Docker Compose to Kubernetes manifests |  |  | 2 | 10 |  |  | 500 | done
- | Prepare CloudNativePG |  |  |  | 3 |  |  | 120 | done
- | Launch and setup Argo CD |  |  |  | 1.5 |  |  | 60 | done
- | Migration & Kubernetes |  |  |  | 1 |  |  | 40 | done
- | Work with Redpanda |  |  |  | 1 |  |  | 40 | done
- | Setup Infisical |  |  |  | 1 |  |  | 40 | done
2 | Support | 11 | 2 |  |  |  |  | 335 | done |  |  |  | 12 | 12 |  | 900
- | USDT wallet out-of-sync |  |  |  | 11 |  |  | 440 | done
- | bnb gas tip 0 |  |  |  | 10 |  |  | 400 | done
- | searching for USDT out-of-sync account |  |  |  | 1 |  |  | 40 | done
- | stucked USDT TX in mempool for no reason |  |  |  | 1 |  |  | 40 | done
- | stage hotfix upload |  |  |  | 1 |  |  | 40 | done
- | Transaction started at 22556338 but was not mined within 50 blocks |  |  |  | 1 |  |  | 40 | done
- | clearing docker containers with HEX after changing firewall rules |  |  | 0.5 | 2.5 |  |  | 125 | done
- | research using standards for BNB |  |  |  | 3.5 |  |  | 140 | done
- | production update on 19th May |  |  |  | 1 |  |  | 40 | done
- | Implementation RETH node | 1 | [5 empty] | 25 | done
3 | BA | [6 empty] | 0 | done | 50 | 10 |  |  |  |  | 1550
- | admin quorum: backend, frontend | 8 | 1 |  |  |  |  | 230 | done
- | admin quorum: actions | 4 | 0.5 |  |  |  |  | 115 | done
- | Distingiush .env related for definition hung time for batch and common TXs | 6 | [5 empty] | 150 | done
- | DeskPro integration | 2 | 0.5 |  |  |  |  | 65 | done
- | Do not mix reciever' addresses for batch accumulation in case of changing the address (ex. Batching Combined) | 6 | [5 empty] | 150 | done
- | Improvement on Address visual on Wallets | 6 | [5 empty] | 150 | done
- | Review stucked BTC deposits | 5 | [5 empty] | 125 | done
- | Clear warn logs in deploy.sh | 1 | [5 empty] | 25 | done
- | Trigger accumulation for replaced TXs | 5 | [5 empty] | 125 | done
- | Log each response from the 3rd party service | 3 | [5 empty] | 75 | done
4 | Local deployment of ether-like L1 nodes (added over sprint 2nd of June) |  |  |  | 29 |  |  | 1160 | done |  |  |  | 30 |  |  | 1200
5 | Delete old entries from the outbox table (added over sprint 5nd of June) |  |  |  | 9.5 |  |  | 380 | done |  |  |  | 10 |  |  | 400
[7 empty] | Subtotal | 12695 | [6 empty] | Total | 12180
Added tasks
6 | Switch Etherscan to the v2 API | 1 |  | 0.5 | 9 |  |  | 410 | done
[7 empty] | Subtotal | 410
[7 empty] | Total | 13105

## Sprint 36 (20.06-21.07) (hidden)
№ | Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) | 16 | 30 | 480
2 | Max (PM) | 71 | 25 | 1775
3 | Kostya (Analytic) | 20 | 25 | 500
4 | Philipp (Lead) | 26 | 50 | 1300
5 | Backend developer 1 | 89.5 | 40 | 3580
6 | Backend developer 2 | 30 | 40 | 1200
7 | Backend developer 3 | 42 | 40 | 1680
8 | Frontend developer 1 |  | 35 | 0
9 | Frontend developer 1 |  | 35 | 0
10 | Designer |  | 25 | 0
10515
|  | Actual | [6 empty] | Status | Estimation
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Actual price, $ |  | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $
1 | Horizontal scaling | [6 empty] | 0 | done | [6 empty] | 0
- | Reverse proxy for distributing requests between providers |  |  |  | 5 |  |  | 200 | done |  |  |  | 18 |  |  | 720
- | Improvements to migrate.ts in the blockchain service |  |  |  | 0 |  |  | 0 | canceled |  |  |  | 12 |  |  | 480
- | Switching to connectrpc |  |  |  | 0 |  |  | 0 | canceled |  |  |  | 5 |  |  | 200
2 | DevOps (2) | [6 empty] | 0 | done |  | 2 | 8 | 70 |  |  | 3260
- | Deployment - Local test deployment completed - Backend service assembly issue resolved - Resource synchronization issues with cloudnativepg fixed |  | 1 | 5 | 22 |  |  | 1160 | done | [6 empty] | 0
- | Ansible playbooks for cluster management - Infrastructure architecture of the system designed for correct operation in two environments (staging and production) - Correct namespace partitioning defined for optimal resource organization - K3s cluster installed with master and worker nodes on specified hosts - Node annotation system configured with labels (infrastructure/workload) - Implemented the ability to dynamically add nodes without interrupting cluster operation - API server TLS certificate update process configured via Ansible - Cluster backup system integrated using Velero and S3-compatible backend - Centralized variable structure and clear role separation in Ansible organized - Validation of cluster availability and operability after all operations |  |  | 6 | 18.5 |  |  | 1040 | done | [6 empty] | 0
- | Transferring Docker Compose to Kubernetes manifests |  |  |  | 7.5 |  |  | 300 | done | [6 empty] | 0
- | Preparing CloudNativePG |  |  |  | 3.5 |  |  | 140 | done | [6 empty] | 0
- | Installing and configuring Argo CD |  |  |  | 1 |  |  | 40 | done | [6 empty] | 0
- | Migrations and Kubernetes - Configuring manifests to run migrations in k8s |  |  |  | 1 |  |  | 40 | done | [6 empty] | 0
- | Redpanda |  |  |  | 1.5 |  |  | 60 | done | [6 empty] | 0
- | Configuring Infisical and setting up secrets and methods for working with them in: - postgreSQL - Redis - infisical itself Configuring access and ensuring security; Error handling and ensuring fault tolerance |  |  | 1 | 8.5 |  |  | 390 | done | [6 empty] | 0
- | Transferring grafana dashboards |  |  |  | 5.5 |  |  | 220 | done | [6 empty] | 0
- | Configuring metrics collection (openTelemetry Collector, prometheus, jaeger) - Installed Jaeger in a Kubernetes cluster using manifests - Configured persistent trace storage with backend parameter configuration - Created PVC for storing trace data and provided backup - Deployed Prometheus with all necessary exporters (including Blackbox Exporter) - Developed scripts for automatic generation of configuration files template-based - Implemented a mechanism for managing environment variables via Kubernetes Secrets and ConfigMaps - Configured OpenTelemetry Collector using the Helm chart from the official repository - Configured receivers, processors and exporters for integration with Jaeger - Defined service pipelines for traces, metrics and logs - Provided automatic restart of services when changing configurations - Implemented secure configuration via ConfigMap and Kubernetes Secrets - Configured access control to the UI and API of monitoring systems |  |  | 4 | 13.5 |  |  | 740 | done | [6 empty] | 0
3 | Testing | 29 | 5 |  |  |  |  | 875 | done | 40 | 5 |  |  |  |  | 1150
4 | BA | [6 empty] | 0 | done | 50 | 5 |  |  |  |  | 1400
- | Admin Quorum | 7 | 4 |  |  |  |  | 295 | done | [6 empty] | 0
- | MPC | 6 | 4 |  |  |  |  | 270 | done | [6 empty] | 0
- | Runbook | 2 | 2 |  |  |  |  | 110 | done | [6 empty] | 0
- | Search button in Tools->Wallets. Optimization. Requests changes | 5 | [5 empty] | 125 | done | [6 empty] | 0
- | Change the method of recording fees for batch transactions | 3 | [5 empty] | 75 | done | [6 empty] | 0
- | [MAU-237] Sort all lists alphabetically | 1 | [5 empty] | 25 | done | [6 empty] | 0
- | Enter 24-hour time format regardless of browser time zone and set time zone to UTC+0 | 2 | [5 empty] | 50 | done | [6 empty] | 0
- | [MAU-209] Add address viewing and the ability to download wallet addresses in CSV | 5 | [5 empty] | 125 | done | [6 empty] | 0
- | Document all env files | 2 | [5 empty] | 50 | done | [6 empty] | 0
5 | Help Desk & Technical stuff | [6 empty] | 0 | done |  |  |  | 12 | 12 |  | 960
- | [MAU-256] Investigating bnb gas tip 0 error when some logs are missing | 4 |  | 0.5 | 9.5 |  |  | 505 | done | [6 empty] | 0
- | [MAU-260] doge deposits & accums issues | 6 |  | 0.5 | 16.5 |  |  | 835 | done | [6 empty] | 0
- | [MAU-?][06/24] Investigating stuck BCH transactions | 4 |  | 4 | 14.5 |  |  | 880 | done | [6 empty] | 0
- | [MAU-?] Tron've stuck in pending status but have block | 3 |  |  | 7 |  |  | 355 | done | [6 empty] | 0
- | [MAU-?] Prod issues 06/29 | 7.5 |  | 3 | 10 |  |  | 737.5 | done | [6 empty] | 0
- | [MAU-?] Technical help desk (36) | 4.5 |  | 2 | 16.5 |  |  | 872.5 | done | [6 empty] | 0
[7 empty] | Total | 10515 | [6 empty] | Total | 8170

## Sprint 37 (22.07-29.08) (hidden)
№ | Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) | 5.5 | 30 | 165
2 | Max (PM) | 88 | 25 | 2200
3 | Kostya (Analytic) |  | 25 | 0
4 | Philipp (Lead) | 14 | 50 | 700
5 | Backend developer 1 | 165 | 40 | 6600
6 | Backend developer 2 | 54 | 40 | 2160
7 | Backend developer 3 |  | 40 | 0
8 | Frontend developer 1 |  | 35 | 0
9 | Frontend developer 1 |  | 35 | 0
10 | Designer |  | 25 | 0
11825
|  | Actual | [6 empty] | Status | Estimation
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Actual price, $ |  | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $
1 | DevOps (3) | [6 empty] | 0 | done |  |  |  | 55 |  |  | 2200
- | Deployment - Stage deployment completed - Demo calls - Environment variables migrated from old staging environment - System performance issues with large number of updates fixed - Comprehensive system testing completed |  | 1 | 6 | 27.5 |  |  | 1430 | done | [6 empty] | 0
- | GitLab and CI/CD - Update scripts have been adapted for use in CI/CD (initially they were only for manual use) - Procedures for updating the system on a staging environment have been defined |  |  | 0.5 | 17.5 |  |  | 725 | done | [6 empty] | 0
- | Connecting external graylog to k3s |  |  |  | 4 |  |  | 160 | done | [6 empty] | 0
- | Load testing on cpu at k3s-server |  |  | 2 | 11.5 |  |  | 560 | done | [6 empty] | 0
- | Optimizing the performance and stability of the infrastructure in the DBMS |  |  |  | 5 |  |  | 200 | done | [6 empty] | 0
- | Add a playbook to add a new node |  |  |  | 5 |  |  | 200 | done | [6 empty] | 0
- | Renaming system's parts - SERVER, CLIENT vs BACKEND, FRONTEND |  |  |  | 0.5 |  |  | 20 | done | [6 empty] | 0
- | Grafana alerts setup |  |  |  | 5 |  |  | 200 | done | [6 empty] | 0
- | Developing a kubectl script for working with the DB |  |  |  | 5 |  |  | 200 | done | [6 empty] | 0
- | Splitting repositories |  |  |  | 1 |  |  | 40 | done | [6 empty] | 0
- | Add initCointainers for checking kafka |  |  |  | 1 |  |  | 40 | done | [6 empty] | 0
- | Transition to runtime environment variables |  |  |  | 3 |  |  | 120 | done | [6 empty] | 0
- | Optimization of the configuration of environment variables and improvement of the usability of the monitoring system - Configured the transfer of variables for Prometheus and Blackbox-exporter - Eliminated duplication of variables - all settings are managed from one place - Protected variables in the frontend image with the ability to change them at startup - Combined scripts for ease of use of the system - Simplified administration - eliminated the need to make changes in several places |  |  | 3 | 15.5 |  |  | 770 | done | [6 empty] | 0
- | Add container restart via New Worker |  |  |  | 3.5 |  |  | 140 | done | [6 empty] | 0
- | Optimization of background account search |  |  | 0.5 | 13 |  |  | 545 | done | [6 empty] | 0
- | Split service migrations to preserve the startup order |  |  | 1 | 9.5 |  |  | 430 | done | [6 empty] | 0
- | Configuring the log format in graylog - Configured the correct log format for the Fluent-bit service - Resolved compatibility issues with the existing logging system - Ensured correct integration of logs into the overall monitoring infrastructure |  |  |  | 11 |  |  | 440 | done | [6 empty] | 0
- | Configure ArgoCD operation via jumpbox |  |  |  | 5 |  |  | 200 | done | [6 empty] | 0
- | Fix k8s metrics exporter |  |  |  | 2.5 |  |  | 100 | done | [6 empty] | 0
- | Nodejs metrics for all nodejs containers |  |  |  | 5 |  |  | 200 | done | [6 empty] | 0
- | Optimize RAM consumption and the number of active connections |  |  |  | 3.5 |  |  | 140 | done | [6 empty] | 0
- | Configure Rolling update for all grpc services |  |  |  | 1.5 |  |  | 60 | done | [6 empty] | 0
- | Create a Readonly ArgoCD user |  |  |  | 4 |  |  | 160 | done | [6 empty] | 0
- | Preparing instructions for updating the system - updating code and images - updating the application in argoCD - updating secrets - synchronizing argoCD with the repository - synchronizing infisical - measuring and comparing metrics with the transition of the system to k8s |  |  |  | 20 |  |  | 800 | done | [6 empty] | 0
- | Moving kafka comsumer to workers |  |  |  | 2 |  |  | 80 | done | [6 empty] | 0
- | Moving notifications migrations to a separate service |  |  |  | 2.5 |  |  | 100 | done | [6 empty] | 0
- | The scanner accumulates mempool transactions |  |  |  | 4 |  |  | 160 | done | [6 empty] | 0
- | Problem with receiving a transaction from the provider |  |  |  | 3 |  |  | 120 | done | [6 empty] | 0
2 | Testing | 32 | 4.5 |  |  |  |  | 935 | done | 40 | 5 |  |  |  |  | 1150
3 | BA | [6 empty] | 0 | done | 50 | 5 |  |  |  |  | 1400
- | MPC | 2 | [5 empty] | 50 | done | [6 empty] | 0
- | Runbook | 4 | [5 empty] | 100 | done | [6 empty] | 0
- | [MAU-235] Allow changing the accumulation address and completing transaction collection for a batch in case of address change | 8 | [5 empty] | 200 | done | [6 empty] | 0
- | Cache the fee to avoid hitting the request limit when multiple retries are made | 2 | [5 empty] | 50 | done | [6 empty] | 0
- | Split the `unsent` transactions graph for payouts and accumulations | 0.5 | [5 empty] | 12.5 | done | [6 empty] | 0
- | Betterstack alternatives for monitoring the system | 4.5 | [5 empty] | 112.5 | done | [6 empty] | 0
- | Flexible batch accumulations and payouts | 6.5 | [5 empty] | 162.5 | done | [6 empty] | 0
- | Add copy and redirect to the BC explorer buttons for hash and address | 2.5 | [5 empty] | 62.5 | done | [6 empty] | 0
- | In Grafana add monitoring to find stucked block | 2.5 | [5 empty] | 62.5 | done | [6 empty] | 0
- | Accumulation simple rework - add hash TXs column and remove not unique NF | 2.5 | [5 empty] | 62.5 | done | [6 empty] | 0
- | Button `push Batch TX` | 2 | [5 empty] | 50 | done | [6 empty] | 0
- | Display fraud attempts on the UI as we show duplicate | 3 | [5 empty] | 75 | done | [6 empty] | 0
- | add system's handling of emergency situations (related with kafka and handling mempool txs) | 8 | [5 empty] | 200 | done | [6 empty] | 0
4 | Help Desk & Technical stuff | [6 empty] | 0 | done |  |  |  | 12 | 12 |  | 960
- | Extension of the type for transaction id in the scanner DB | 0.5 |  |  | 2.5 |  |  | 112.5 | done | [6 empty] | 0
- | Incorrect work with kafka | 0.5 |  |  | 5 |  |  | 212.5 | done | [6 empty] | 0
- | Error when processing a failed transaction covering several transfers | 0.5 |  |  | 3 |  |  | 132.5 | done | [6 empty] | 0
- | Cleaning the prod from unused tokens | 1.5 |  |  | 3 |  |  | 157.5 | done | [6 empty] | 0
- | Bitcoin-like transactions do not return mempool transactions | 0.5 |  | 0.5 | 1.5 |  |  | 97.5 | done | [6 empty] | 0
- | Failed payments block kafka handlers | 3 |  |  | 7 |  |  | 355 | done | [6 empty] | 0
- | 13.08 Problems with nonce on the prod | 2 |  |  | 4 |  |  | 210 | done | [6 empty] | 0
- | Prepare requests to change accumulation statuses | 0.5 |  |  | 1.5 |  |  | 72.5 | done | [6 empty] | 0
[7 empty] | Total | 11825 | [6 empty] | Total | 5710

## Sprint 43 (24.03 - 27.04)
№ | Employee | Actual hours | Price $/hour | Final price, $
1 | Alexey (Lead PM) |  |  | 0
2 | Max (PM) |  |  | 0
3 | Nick (Analytic) |  |  | 0
4 | Philipp (Lead) |  |  | 0
5 | Backend developer 1 |  |  | 0
6 | Backend developer 2 |  |  | 0
7 | Frontend developer 1 |  |  | 0
8 | Frontend developer 1 |  |  | 0
9 | Designer |  |  | 0
0
Estimation
№ | Task | PM, Analytic | Lead PM | Lead | Backend developer | Frontend developer | Designer | Estimate price, $
1 | MPC adoptation in BPS
- | Modify wallet's model to add MPC properties |  |  |  | 12
| Modify logic to work with MPC in BPS - Public keys generation using Shamir's algorythm and MPC - Signing TXs using Shamir's algorythm and MPC |  |  | 2 | 32
- | Add possibility to create wallet using MPC / Shamir's |  |  |  |  | 12
- | Cover new functionality with additional logs |  |  |  | 4
2 | MPC deploy |  |  | 1 | 40
3 | [Carbono] DBMS backup and restoration process |  |  |  | 0
- | Add MinIO in cluster |  |  | 1 | 6
- | Add `barman-cloud` backup in cluster |  |  | 2 | 12
- | Modify cfg DB to work with backups |  |  |  | 4
- | Create bash-script for start backups on-demand |  |  | 1 | 4
- | Add bash-script for restoring from backup via chosen time (PITR) |  |  | 1 | 8
- | Create docs for periodical test DB restoring on the Stage (runbooks) | 2 |  | 2 | 12
- | Add monitoring MinIO and backups in Grafana using Prometheus |  |  |  | 8
4 | Implement different approach to work with system balances |  |  |  | 21
5 | Add auto `extend`
- | Implement balance notifications within detected differs (BC vs system) |  |  |  | 8
- | Extend exp. backoff functionality for `background fetching` |  |  |  | 18
6 | MPC | 15 |  | 5 | 110
- | Encryption for DB
- | Encryption for transport layer
- | Load-testing & Subsequent optimization
- | Add rotation mechanism for API-key
- | RnD to extend generation & signing sides to 3-of-5 with operator's sign
7 | Business & Technical analysis:
- | Investigate best practices for RBAC & ABAC | 32 | 2
- | Separate accumulator addresses into dedicated table | 8
- | Simplify private key upload for EVM payouts (replace file upload with textarea) | 8
- | Double-entry ledger | 48 | 5
- | Deposit-Payout flow document with diagrams |  |  |  | 20
8 | Continue playwright autotests development
- | One button run | 16
- | Implementation of scanning pending TXs in one button | 16
- | CI/CD Integration | 8
- | [RnD] LLM Auto Test Generation | 8
9 | Help desk & Technical stuff | 32 | 5 | 3 | 30 | 10
10 | Testing | 48 | 5
| Total | 241 | 17 | 18 | 349 | 22 | 0

## Sprint 11 (22.03-08.04) (hidden)
# | Task | Estimate Hours | Estimate Amount, $ | Actual hours | Final price, $ | Status
| Avalanche C-Chain + Avalanche X-Chain swap | 37 |  | 30 | 1200 | Done
| ADA to iancoleman | 5 |  |  | 0 | In progress
| SOL to iancoleman | 9 |  |  | 0 | In progress | Speak with Kirill
| Adding test data for tokens. Changing the test data of the coin by the developer and tokens on the interface | 10 |  | 8 | 320 | Done
| Bug: Delete unnecesarry networks, what doesn't work in Trezor (Avalanche) | 14 |  | 10 | 400 | Done
| Bug: max priority fee and max fee are not updated |  |  | 2 | 80 | Done
|  |  |  | Total: | 2000